## Dashboard
RMF / ATO Management Dashboard
Total Requirements | 177 | RMF Step | Status | Primary Artifact
Requirements Complete | 0 | Prepare | In Progress | Boundary / Strategy
Evidence Complete | 0 | Categorize | Not Started | Categorization Report
Open POA&M Items | 100 | Select | Not Started | Control Matrix
Critical / High POA&M Open | 50 | Implement | In Progress | SSP / Evidence
IATT Blockers | 30 | Assess | Not Started | SAP / SAR
ATO Blockers | 60 | Authorize | Not Started | IATT / ATO Package
IATT Target | 2027-03-31 | Monitor | Not Started | ConMon / POA&M
ATO Target | 2027-10-09
Overall Readiness | Red

## AO Brief
Flight Test System RMF Implementation – AO Brief
Mission Objective
Implement a secure, testable, and evidence-driven system authorization path with two major milestones: Interim Authorization to Test (IATT) and Authorization to Operate (ATO).
Authorization Strategy
IATT authorizes controlled testing using an initial RMF package, defined test scope, initial control evidence, and a POA&M capturing known risk. ATO authorizes full operations after final assessment, closure or acceptance of residual findings, and activation of continuous monitoring.
Decision Gates
IATT Gate: boundary defined; initial System Security Plans (SSP), Security Assessment Plans (SAP), Security Assessment Reports (SAR); Information Sharing Architecture (ISA), and Interface Control Documents (ICD) drafts. These are foundational components to the Risk Management Framework (RMF) drafts, initial scans, POA&M, and risk acceptance for test scope.
ATO Gate: final SSP/SAR; no unresolved critical/high findings without acceptance; ConMon active; incident response and configuration management validated; residual risk accepted.
Evidence Model
Every requirement is linked to controls, evidence artifacts, CDRLs, IMS activities, risks, and POA&M triggers. This supports traceability from SOO objective to AO decision package.
Management Mechanism
Dashboard, Evidence Tracker, POA&M Automation, IATT Gate, ATO Gate, IMS, CDRL Linkage, and Source Selection tabs provide integrated execution control.

## RMF Process
RMF Step | Objective | Key Activities | Primary Artifacts | IATT Contribution | ATO Contribution
Prepare | Establish governance and authorization context | Identify AO, ISSM/ISSO, boundary, roles, system mission, and cyber schedule | RMF Strategy; Boundary Diagram | Defines test boundary and stakeholders | Defines operational authorization scope
Categorize | Determine information impact level | Assess confidentiality, integrity, and availability impacts | Security Categorization Report | Confirms test environment impact assumptions | Confirms operational impact baseline
Select | Select and tailor controls | Apply baseline controls and overlays; document tailoring rationale | Control Selection Matrix | Identifies minimum test controls | Defines full operational control set
Implement | Build and document controls | Implement encryption, logging, access, hardening, monitoring, interfaces, and CM | SSP; Evidence Artifacts | Shows minimum control implementation for testing | Shows full control implementation
Assess | Validate controls | Plan and execute assessment, scans, STIG checks, and control tests | SAP; SAR; Scan Results | Supports IATT risk decision | Supports ATO risk decision
Authorize | Make risk decision | Assemble package, brief AO, capture conditions and residual risk | IATT/ATO Decision Package | AO grants IATT or conditions | AO grants ATO or conditional ATO
Monitor | Maintain authorization | Operate scans, POA&M, logs, incident response, changes, and reporting | ConMon Reports; POA&M | Tracks IATT conditions | Maintains ATO

## Requirements
Req ID | Category | RMF Step | Requirement Statement | Priority | NIST Control(s) | Verification | Acceptance Criteria | Evidence Artifact | IATT Required | ATO Required | Status | Linked IMS Task | Linked CDRL | Linked Risk | POA&M Trigger
FTN-001 | Flight Test Network | Implement | The system shall provide a standalone mission network capable of supporting flight and ground test operations in connected and disconnected modes with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-7; SC-8 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-001. | EV-001 | Yes | Yes | In Progress | IMS-001 | A001 | R-001 | Yes
FTN-002 | Flight Test Network | Implement | The system shall ingest, time-align, and retain telemetry, sensor, range safety, and system status data from all approved sources with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-8; SC-45 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-002. | EV-002 | Yes | Yes | In Progress | IMS-002 | A002 | R-002 | Yes
FTN-003 | Flight Test Network | Implement | The system shall transfer post-event test data to the Authoritative Source of Truth with checksum validation and no unauthorized modification with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-45; AU-2 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-003. | EV-003 | Yes | Yes | In Progress | IMS-003 | A003 | R-003 | Yes
FTN-004 | Flight Test Network | Implement | The system shall maintain authoritative time synchronization across network nodes within mission-defined tolerance with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AU-2; SI-4 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-004. | EV-004 | Yes | Yes | In Progress | IMS-004 | A004 | R-004 | Yes
FTN-005 | Flight Test Network | Implement | The system shall support network administration, maintenance, and secure configuration of all flight test network components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-4; CM-2 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-005. | EV-005 | Yes | Yes | Not Started | IMS-005 | A005 | R-005 | Yes
FTN-006 | Flight Test Network | Implement | The system shall support firmware and software distribution to approved test systems with configuration baseline traceability with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CM-2; SC-7 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-006. | EV-006 | Yes | Yes | In Progress | IMS-006 | A006 | R-006 | Yes
FTN-007 | Flight Test Network | Implement | The system shall provide a standalone mission network capable of supporting flight and ground test operations in connected and disconnected modes with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-7; SC-8 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-007. | EV-007 | Yes | Yes | In Progress | IMS-007 | A007 | R-007 | Yes
FTN-008 | Flight Test Network | Implement | The system shall ingest, time-align, and retain telemetry, sensor, range safety, and system status data from all approved sources with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-8; SC-45 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-008. | EV-008 | Yes | Yes | In Progress | IMS-008 | A008 | R-008 | Yes
FTN-009 | Flight Test Network | Implement | The system shall transfer post-event test data to the Authoritative Source of Truth with checksum validation and no unauthorized modification with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-45; AU-2 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-009. | EV-009 | Yes | Yes | In Progress | IMS-009 | A009 | R-009 | Yes
FTN-010 | Flight Test Network | Implement | The system shall maintain authoritative time synchronization across network nodes within mission-defined tolerance with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AU-2; SI-4 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-010. | EV-010 | Yes | Yes | Not Started | IMS-010 | A010 | R-010 | Yes
FTN-011 | Flight Test Network | Implement | The system shall support network administration, maintenance, and secure configuration of all flight test network components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-4; CM-2 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-011. | EV-011 | Yes | Yes | In Progress | IMS-011 | A011 | R-011 | Yes
FTN-012 | Flight Test Network | Implement | The system shall support firmware and software distribution to approved test systems with configuration baseline traceability with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CM-2; SC-7 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-012. | EV-012 | Yes | Yes | In Progress | IMS-012 | A012 | R-012 | Yes
FTN-013 | Flight Test Network | Implement | The system shall provide a standalone mission network capable of supporting flight and ground test operations in connected and disconnected modes with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-7; SC-8 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-013. | EV-013 | Yes | Yes | In Progress | IMS-013 | A013 | R-013 | Yes
FTN-014 | Flight Test Network | Implement | The system shall ingest, time-align, and retain telemetry, sensor, range safety, and system status data from all approved sources with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-8; SC-45 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-014. | EV-014 | Yes | Yes | In Progress | IMS-014 | A014 | R-014 | Yes
FTN-015 | Flight Test Network | Implement | The system shall transfer post-event test data to the Authoritative Source of Truth with checksum validation and no unauthorized modification with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-45; AU-2 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-015. | EV-015 | Yes | Yes | Not Started | IMS-015 | A015 | R-015 | Yes
FTN-016 | Flight Test Network | Implement | The system shall maintain authoritative time synchronization across network nodes within mission-defined tolerance with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AU-2; SI-4 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-016. | EV-016 | Yes | Yes | In Progress | IMS-016 | A016 | R-016 | Yes
FTN-017 | Flight Test Network | Implement | The system shall support network administration, maintenance, and secure configuration of all flight test network components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-4; CM-2 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-017. | EV-017 | Yes | Yes | In Progress | IMS-001 | A017 | R-017 | Yes
FTN-018 | Flight Test Network | Implement | The system shall support firmware and software distribution to approved test systems with configuration baseline traceability with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CM-2; SC-7 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-018. | EV-018 | Yes | Yes | In Progress | IMS-002 | A018 | R-018 | Yes
FTN-019 | Flight Test Network | Implement | The system shall provide a standalone mission network capable of supporting flight and ground test operations in connected and disconnected modes with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-7; SC-8 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-019. | EV-019 | Yes | Yes | In Progress | IMS-003 | A001 | R-019 | Yes
FTN-020 | Flight Test Network | Implement | The system shall ingest, time-align, and retain telemetry, sensor, range safety, and system status data from all approved sources with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-8; SC-45 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-020. | EV-020 | Yes | Yes | Not Started | IMS-004 | A002 | R-020 | Yes
FTN-021 | Flight Test Network | Implement | The system shall transfer post-event test data to the Authoritative Source of Truth with checksum validation and no unauthorized modification with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-45; AU-2 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-021. | EV-021 | Yes | Yes | In Progress | IMS-005 | A003 | R-021 | Yes
FTN-022 | Flight Test Network | Implement | The system shall maintain authoritative time synchronization across network nodes within mission-defined tolerance with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AU-2; SI-4 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-022. | EV-022 | Yes | Yes | In Progress | IMS-006 | A004 | R-022 | Yes
FTN-023 | Flight Test Network | Implement | The system shall support network administration, maintenance, and secure configuration of all flight test network components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-4; CM-2 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-023. | EV-023 | Yes | Yes | In Progress | IMS-007 | A005 | R-023 | Yes
FTN-024 | Flight Test Network | Implement | The system shall support firmware and software distribution to approved test systems with configuration baseline traceability with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CM-2; SC-7 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-024. | EV-024 | Yes | Yes | In Progress | IMS-008 | A006 | R-024 | Yes
FN-001 | Factory Network | Implement | The system shall provide a secure factory test environment for development, integration, certification, and release of software and firmware with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-2; CM-6 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-025 | Yes | Yes | Not Started | IMS-009 | A007 | R-025 | Yes
FN-002 | Factory Network | Implement | The system shall validate software and firmware artifacts prior to release using approved build, test, and certification records with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-6; SC-8 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-026 | Yes | Yes | In Progress | IMS-010 | A008 | R-026 | Yes
FN-003 | Factory Network | Implement | The system shall support disconnected lab maintenance machines for controlled update of test equipment with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-8; SC-28 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-027 | Yes | Yes | In Progress | IMS-011 | A009 | R-027 | Yes
FN-004 | Factory Network | Implement | The system shall maintain configuration control and rollback capability for all factory network components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-28; SA-11 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-028 | Yes | Yes | In Progress | IMS-012 | A010 | R-028 | Yes
FN-005 | Factory Network | Implement | The system shall support secure transfer of certified artifacts to operational test environments with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SA-11; AC-3 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-029 | Yes | Yes | In Progress | IMS-013 | A011 | R-029 | Yes
FN-006 | Factory Network | Implement | The system shall provide a secure factory test environment for development, integration, certification, and release of software and firmware with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | AC-3; CM-2 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-030 | Yes | Yes | Not Started | IMS-014 | A012 | R-030 | Yes
FN-007 | Factory Network | Implement | The system shall validate software and firmware artifacts prior to release using approved build, test, and certification records with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-2; CM-6 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-031 | Yes | Yes | In Progress | IMS-015 | A013 | R-031 | Yes
FN-008 | Factory Network | Implement | The system shall support disconnected lab maintenance machines for controlled update of test equipment with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-6; SC-8 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-032 | Yes | Yes | In Progress | IMS-016 | A014 | R-032 | Yes
FN-009 | Factory Network | Implement | The system shall maintain configuration control and rollback capability for all factory network components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-8; SC-28 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-033 | Yes | Yes | In Progress | IMS-001 | A015 | R-033 | Yes
FN-010 | Factory Network | Implement | The system shall support secure transfer of certified artifacts to operational test environments with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-28; SA-11 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-034 | Yes | Yes | In Progress | IMS-002 | A016 | R-034 | Yes
FN-011 | Factory Network | Implement | The system shall provide a secure factory test environment for development, integration, certification, and release of software and firmware with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SA-11; AC-3 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-035 | Yes | Yes | Not Started | IMS-003 | A017 | R-035 | Yes
FN-012 | Factory Network | Implement | The system shall validate software and firmware artifacts prior to release using approved build, test, and certification records with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | AC-3; CM-2 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-036 | Yes | Yes | In Progress | IMS-004 | A018 | R-036 | Yes
FN-013 | Factory Network | Implement | The system shall support disconnected lab maintenance machines for controlled update of test equipment with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-2; CM-6 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-037 | Yes | Yes | In Progress | IMS-005 | A001 | R-037 | Yes
FN-014 | Factory Network | Implement | The system shall maintain configuration control and rollback capability for all factory network components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-6; SC-8 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-038 | Yes | Yes | In Progress | IMS-006 | A002 | R-038 | Yes
FN-015 | Factory Network | Implement | The system shall support secure transfer of certified artifacts to operational test environments with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-8; SC-28 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-039 | Yes | Yes | In Progress | IMS-007 | A003 | R-039 | Yes
FN-016 | Factory Network | Implement | The system shall provide a secure factory test environment for development, integration, certification, and release of software and firmware with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-28; SA-11 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-040 | Yes | Yes | Not Started | IMS-008 | A004 | R-040 | Yes
FN-017 | Factory Network | Implement | The system shall validate software and firmware artifacts prior to release using approved build, test, and certification records with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SA-11; AC-3 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-041 | Yes | Yes | In Progress | IMS-009 | A005 | R-041 | Yes
FN-018 | Factory Network | Implement | The system shall support disconnected lab maintenance machines for controlled update of test equipment with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | AC-3; CM-2 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-042 | Yes | Yes | In Progress | IMS-010 | A006 | R-042 | Yes
FN-019 | Factory Network | Implement | The system shall maintain configuration control and rollback capability for all factory network components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-2; CM-6 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-043 | Yes | Yes | In Progress | IMS-011 | A007 | R-043 | Yes
FN-020 | Factory Network | Implement | The system shall support secure transfer of certified artifacts to operational test environments with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-6; SC-8 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-044 | Yes | Yes | In Progress | IMS-012 | A008 | R-044 | Yes
FN-021 | Factory Network | Implement | The system shall provide a secure factory test environment for development, integration, certification, and release of software and firmware with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-8; SC-28 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-045 | Yes | Yes | Not Started | IMS-013 | A009 | R-045 | Yes
FN-022 | Factory Network | Implement | The system shall validate software and firmware artifacts prior to release using approved build, test, and certification records with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-28; SA-11 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-046 | Yes | Yes | In Progress | IMS-014 | A010 | R-046 | Yes
DEE-001 | Digital Engineering Environment | Implement | The system shall host authoritative technical data, models, artifacts, and engineering knowledge needed to support digital thread traceability with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AC-3; IA-2 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-047. | EV-047 | Yes | Yes | In Progress | IMS-015 | A011 | R-047 | Yes
DEE-002 | Digital Engineering Environment | Implement | The system shall provide common data model relationships between requirements, design, test, certification, and sustainment artifacts with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | IA-2; SC-28 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-048. | EV-048 | Yes | Yes | In Progress | IMS-016 | A012 | R-048 | Yes
DEE-003 | Digital Engineering Environment | Implement | The system shall provide multi-tenant storage, cataloging, search, and retrieval of test and engineering data with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-28; SI-10 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-049. | EV-049 | Yes | Yes | In Progress | IMS-001 | A013 | R-049 | Yes
DEE-004 | Digital Engineering Environment | Implement | The system shall support edge node synchronization where authorized users require distributed access with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-10; AU-12 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-050. | EV-050 | Yes | Yes | Not Started | IMS-002 | A014 | R-050 | Yes
DEE-005 | Digital Engineering Environment | Implement | The system shall enforce role-based access controls for all users and data domains with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AU-12; PL-8 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-051. | EV-051 | Yes | Yes | In Progress | IMS-003 | A015 | R-051 | Yes
DEE-006 | Digital Engineering Environment | Implement | The system shall host authoritative technical data, models, artifacts, and engineering knowledge needed to support digital thread traceability with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | PL-8; AC-3 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-052. | EV-052 | No | Yes | In Progress | IMS-004 | A016 | R-052 | Yes
DEE-007 | Digital Engineering Environment | Implement | The system shall provide common data model relationships between requirements, design, test, certification, and sustainment artifacts with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AC-3; IA-2 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-053. | EV-053 | No | Yes | In Progress | IMS-005 | A017 | R-053 | Yes
DEE-008 | Digital Engineering Environment | Implement | The system shall provide multi-tenant storage, cataloging, search, and retrieval of test and engineering data with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | IA-2; SC-28 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-054. | EV-054 | No | Yes | In Progress | IMS-006 | A018 | R-054 | Yes
DEE-009 | Digital Engineering Environment | Implement | The system shall support edge node synchronization where authorized users require distributed access with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-28; SI-10 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-055. | EV-055 | No | Yes | Not Started | IMS-007 | A001 | R-055 | Yes
DEE-010 | Digital Engineering Environment | Implement | The system shall enforce role-based access controls for all users and data domains with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-10; AU-12 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-056. | EV-056 | No | Yes | In Progress | IMS-008 | A002 | R-056 | Yes
DEE-011 | Digital Engineering Environment | Implement | The system shall host authoritative technical data, models, artifacts, and engineering knowledge needed to support digital thread traceability with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AU-12; PL-8 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-057. | EV-057 | No | Yes | In Progress | IMS-009 | A003 | R-057 | Yes
DEE-012 | Digital Engineering Environment | Implement | The system shall provide common data model relationships between requirements, design, test, certification, and sustainment artifacts with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | PL-8; AC-3 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-058. | EV-058 | No | Yes | In Progress | IMS-010 | A004 | R-058 | Yes
DEE-013 | Digital Engineering Environment | Implement | The system shall provide multi-tenant storage, cataloging, search, and retrieval of test and engineering data with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AC-3; IA-2 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-059. | EV-059 | No | Yes | In Progress | IMS-011 | A005 | R-059 | Yes
DEE-014 | Digital Engineering Environment | Implement | The system shall support edge node synchronization where authorized users require distributed access with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | IA-2; SC-28 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-060. | EV-060 | No | Yes | Not Started | IMS-012 | A006 | R-060 | Yes
DEE-015 | Digital Engineering Environment | Implement | The system shall enforce role-based access controls for all users and data domains with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-28; SI-10 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-061. | EV-061 | No | Yes | In Progress | IMS-013 | A007 | R-061 | Yes
DEE-016 | Digital Engineering Environment | Implement | The system shall host authoritative technical data, models, artifacts, and engineering knowledge needed to support digital thread traceability with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-10; AU-12 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-062. | EV-062 | No | Yes | In Progress | IMS-014 | A008 | R-062 | Yes
DEE-017 | Digital Engineering Environment | Implement | The system shall provide common data model relationships between requirements, design, test, certification, and sustainment artifacts with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AU-12; PL-8 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-063. | EV-063 | No | Yes | In Progress | IMS-015 | A009 | R-063 | Yes
DEE-018 | Digital Engineering Environment | Implement | The system shall provide multi-tenant storage, cataloging, search, and retrieval of test and engineering data with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | PL-8; AC-3 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-064. | EV-064 | No | Yes | In Progress | IMS-016 | A010 | R-064 | Yes
DEE-019 | Digital Engineering Environment | Implement | The system shall support edge node synchronization where authorized users require distributed access with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AC-3; IA-2 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-065. | EV-065 | No | Yes | Not Started | IMS-001 | A011 | R-065 | Yes
DEE-020 | Digital Engineering Environment | Implement | The system shall enforce role-based access controls for all users and data domains with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | IA-2; SC-28 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-066. | EV-066 | No | Yes | In Progress | IMS-002 | A012 | R-066 | Yes
DEE-021 | Digital Engineering Environment | Implement | The system shall host authoritative technical data, models, artifacts, and engineering knowledge needed to support digital thread traceability with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-28; SI-10 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-067. | EV-067 | No | Yes | In Progress | IMS-003 | A013 | R-067 | Yes
DEE-022 | Digital Engineering Environment | Implement | The system shall provide common data model relationships between requirements, design, test, certification, and sustainment artifacts with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-10; AU-12 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-068. | EV-068 | No | Yes | In Progress | IMS-004 | A014 | R-068 | Yes
DEE-023 | Digital Engineering Environment | Implement | The system shall provide multi-tenant storage, cataloging, search, and retrieval of test and engineering data with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AU-12; PL-8 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-069. | EV-069 | No | Yes | In Progress | IMS-005 | A015 | R-069 | Yes
DATA-001 | Data Repository / ASoT | Implement | The system shall ingest data from standalone sources, test sets, repositories, and approved external feeds with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-28; SC-8 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-070. | EV-070 | Yes | Yes | Not Started | IMS-006 | A016 | R-070 | Yes
DATA-002 | Data Repository / ASoT | Implement | The system shall tag, catalog, index, and retain test data so it is searchable by event, source, classification, timestamp, and artifact type with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-8; AU-9 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-071. | EV-071 | Yes | Yes | In Progress | IMS-007 | A017 | R-071 | Yes
DATA-003 | Data Repository / ASoT | Implement | The system shall protect data at rest using approved cryptographic mechanisms and auditable key lifecycle controls with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | AU-9; AC-6 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-072. | EV-072 | Yes | Yes | In Progress | IMS-008 | A018 | R-072 | Yes
DATA-004 | Data Repository / ASoT | Implement | The system shall provide repository availability and integrity checks to support post-test analysis and mission reporting with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AC-6; SI-12 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-073. | EV-073 | Yes | Yes | In Progress | IMS-009 | A001 | R-073 | Yes
DATA-005 | Data Repository / ASoT | Implement | The system shall synchronize data across approved repositories and edge nodes with conflict logging with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-12; CP-9 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-074. | EV-074 | Yes | Yes | In Progress | IMS-010 | A002 | R-074 | Yes
DATA-006 | Data Repository / ASoT | Implement | The system shall ingest data from standalone sources, test sets, repositories, and approved external feeds with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CP-9; SC-28 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-075. | EV-075 | No | Yes | Not Started | IMS-011 | A003 | R-075 | Yes
DATA-007 | Data Repository / ASoT | Implement | The system shall tag, catalog, index, and retain test data so it is searchable by event, source, classification, timestamp, and artifact type with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-28; SC-8 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-076. | EV-076 | No | Yes | In Progress | IMS-012 | A004 | R-076 | Yes
DATA-008 | Data Repository / ASoT | Implement | The system shall protect data at rest using approved cryptographic mechanisms and auditable key lifecycle controls with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-8; AU-9 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-077. | EV-077 | No | Yes | In Progress | IMS-013 | A005 | R-077 | Yes
DATA-009 | Data Repository / ASoT | Implement | The system shall provide repository availability and integrity checks to support post-test analysis and mission reporting with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | AU-9; AC-6 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-078. | EV-078 | No | Yes | In Progress | IMS-014 | A006 | R-078 | Yes
DATA-010 | Data Repository / ASoT | Implement | The system shall synchronize data across approved repositories and edge nodes with conflict logging with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AC-6; SI-12 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-079. | EV-079 | No | Yes | In Progress | IMS-015 | A007 | R-079 | Yes
DATA-011 | Data Repository / ASoT | Implement | The system shall ingest data from standalone sources, test sets, repositories, and approved external feeds with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-12; CP-9 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-080. | EV-080 | No | Yes | Not Started | IMS-016 | A008 | R-080 | Yes
DATA-012 | Data Repository / ASoT | Implement | The system shall tag, catalog, index, and retain test data so it is searchable by event, source, classification, timestamp, and artifact type with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CP-9; SC-28 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-081. | EV-081 | No | Yes | In Progress | IMS-001 | A009 | R-081 | Yes
DATA-013 | Data Repository / ASoT | Implement | The system shall protect data at rest using approved cryptographic mechanisms and auditable key lifecycle controls with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-28; SC-8 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-082. | EV-082 | No | Yes | In Progress | IMS-002 | A010 | R-082 | Yes
DATA-014 | Data Repository / ASoT | Implement | The system shall provide repository availability and integrity checks to support post-test analysis and mission reporting with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-8; AU-9 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-083. | EV-083 | No | Yes | In Progress | IMS-003 | A011 | R-083 | Yes
DATA-015 | Data Repository / ASoT | Implement | The system shall synchronize data across approved repositories and edge nodes with conflict logging with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | AU-9; AC-6 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-084. | EV-084 | No | Yes | In Progress | IMS-004 | A012 | R-084 | Yes
DATA-016 | Data Repository / ASoT | Implement | The system shall ingest data from standalone sources, test sets, repositories, and approved external feeds with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AC-6; SI-12 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-085. | EV-085 | No | Yes | Not Started | IMS-005 | A013 | R-085 | Yes
DATA-017 | Data Repository / ASoT | Implement | The system shall tag, catalog, index, and retain test data so it is searchable by event, source, classification, timestamp, and artifact type with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-12; CP-9 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-086. | EV-086 | No | Yes | In Progress | IMS-006 | A014 | R-086 | Yes
DATA-018 | Data Repository / ASoT | Implement | The system shall protect data at rest using approved cryptographic mechanisms and auditable key lifecycle controls with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CP-9; SC-28 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-087. | EV-087 | No | Yes | In Progress | IMS-007 | A015 | R-087 | Yes
DATA-019 | Data Repository / ASoT | Implement | The system shall provide repository availability and integrity checks to support post-test analysis and mission reporting with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-28; SC-8 | Demonstrate | Successful demonstrate confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-088. | EV-088 | No | Yes | In Progress | IMS-008 | A016 | R-088 | Yes
DATA-020 | Data Repository / ASoT | Implement | The system shall synchronize data across approved repositories and edge nodes with conflict logging with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-8; AU-9 | Analyze | Successful analyze confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-089. | EV-089 | No | Yes | In Progress | IMS-009 | A017 | R-089 | Yes
DATA-021 | Data Repository / ASoT | Implement | The system shall ingest data from standalone sources, test sets, repositories, and approved external feeds with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | AU-9; AC-6 | Test | Successful test confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-090. | EV-090 | No | Yes | Not Started | IMS-010 | A018 | R-090 | Yes
DATA-022 | Data Repository / ASoT | Implement | The system shall tag, catalog, index, and retain test data so it is searchable by event, source, classification, timestamp, and artifact type with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AC-6; SI-12 | Inspect | Successful inspect confirms capability, data integrity checks pass, logs are retained, and results are linked to evidence artifact EV-091. | EV-091 | No | Yes | In Progress | IMS-011 | A001 | R-091 | Yes
CY-001 | Cybersecurity / RMF | Assess | The system shall implement RMF activities, artifacts, and evidence needed to support IATT and ATO decisions with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Critical | RA-5; CA-2 | Test | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-092 | Yes | Yes | In Progress | IMS-012 | A002 | R-092 | Yes
CY-002 | Cybersecurity / RMF | Assess | The system shall apply selected NIST SP 800-53 controls and document implementation details in the System Security Plan with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Critical | CA-2; CA-7 | Inspect | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-093 | Yes | Yes | In Progress | IMS-013 | A003 | R-093 | Yes
CY-003 | Cybersecurity / RMF | Assess | The system shall identify, scan, triage, and remediate vulnerabilities according to AO-approved timelines with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Critical | CA-7; SI-4 | Demonstrate | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-094 | Yes | Yes | In Progress | IMS-014 | A004 | R-094 | Yes
CY-004 | Cybersecurity / RMF | Assess | The system shall collect, correlate, alert, and retain cybersecurity events from boundary, host, application, and repository components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Critical | SI-4; IR-4 | Analyze | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-095 | Yes | Yes | Not Started | IMS-015 | A005 | R-095 | Yes
CY-005 | Cybersecurity / RMF | Assess | The system shall implement cryptographic protection for data in transit and data at rest with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Critical | IR-4; SC-13 | Test | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-096 | Yes | Yes | In Progress | IMS-016 | A006 | R-096 | Yes
CY-006 | Cybersecurity / RMF | Assess | The system shall maintain a current POA&M for open findings, residual risks, mitigations, owners, and target closure dates with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Critical | SC-13; SC-28 | Inspect | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-097 | Yes | Yes | In Progress | IMS-001 | A007 | R-097 | Yes
CY-007 | Cybersecurity / RMF | Assess | The system shall implement RMF activities, artifacts, and evidence needed to support IATT and ATO decisions with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Critical | SC-28; IA-5 | Demonstrate | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-098 | Yes | Yes | In Progress | IMS-002 | A008 | R-098 | Yes
CY-008 | Cybersecurity / RMF | Assess | The system shall apply selected NIST SP 800-53 controls and document implementation details in the System Security Plan with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Critical | IA-5; RA-5 | Analyze | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-099 | Yes | Yes | In Progress | IMS-003 | A009 | R-099 | Yes
CY-009 | Cybersecurity / RMF | Assess | The system shall identify, scan, triage, and remediate vulnerabilities according to AO-approved timelines with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | RA-5; CA-2 | Test | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-100 | Yes | Yes | Not Started | IMS-004 | A010 | R-100 | Yes
CY-010 | Cybersecurity / RMF | Assess | The system shall collect, correlate, alert, and retain cybersecurity events from boundary, host, application, and repository components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CA-2; CA-7 | Inspect | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-101 | Yes | Yes | In Progress | IMS-005 | A011 | R-101 | Yes
CY-011 | Cybersecurity / RMF | Assess | The system shall implement cryptographic protection for data in transit and data at rest with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CA-7; SI-4 | Demonstrate | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-102 | Yes | Yes | In Progress | IMS-006 | A012 | R-102 | Yes
CY-012 | Cybersecurity / RMF | Assess | The system shall maintain a current POA&M for open findings, residual risks, mitigations, owners, and target closure dates with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SI-4; IR-4 | Analyze | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-103 | Yes | Yes | In Progress | IMS-007 | A013 | R-103 | Yes
CY-013 | Cybersecurity / RMF | Assess | The system shall implement RMF activities, artifacts, and evidence needed to support IATT and ATO decisions with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | IR-4; SC-13 | Test | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-104 | Yes | Yes | In Progress | IMS-008 | A014 | R-104 | Yes
CY-014 | Cybersecurity / RMF | Assess | The system shall apply selected NIST SP 800-53 controls and document implementation details in the System Security Plan with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-13; SC-28 | Inspect | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-105 | Yes | Yes | Not Started | IMS-009 | A015 | R-105 | Yes
CY-015 | Cybersecurity / RMF | Assess | The system shall identify, scan, triage, and remediate vulnerabilities according to AO-approved timelines with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-28; IA-5 | Demonstrate | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-106 | Yes | Yes | In Progress | IMS-010 | A016 | R-106 | Yes
CY-016 | Cybersecurity / RMF | Assess | The system shall collect, correlate, alert, and retain cybersecurity events from boundary, host, application, and repository components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | IA-5; RA-5 | Analyze | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-107 | Yes | Yes | In Progress | IMS-011 | A017 | R-107 | Yes
CY-017 | Cybersecurity / RMF | Assess | The system shall implement cryptographic protection for data in transit and data at rest with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | RA-5; CA-2 | Test | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-108 | Yes | Yes | In Progress | IMS-012 | A018 | R-108 | Yes
CY-018 | Cybersecurity / RMF | Assess | The system shall maintain a current POA&M for open findings, residual risks, mitigations, owners, and target closure dates with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CA-2; CA-7 | Inspect | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-109 | Yes | Yes | In Progress | IMS-013 | A001 | R-109 | Yes
CY-019 | Cybersecurity / RMF | Assess | The system shall implement RMF activities, artifacts, and evidence needed to support IATT and ATO decisions with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CA-7; SI-4 | Demonstrate | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-110 | Yes | Yes | Not Started | IMS-014 | A002 | R-110 | Yes
CY-020 | Cybersecurity / RMF | Assess | The system shall apply selected NIST SP 800-53 controls and document implementation details in the System Security Plan with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-4; IR-4 | Analyze | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-111 | Yes | Yes | In Progress | IMS-015 | A003 | R-111 | Yes
CY-021 | Cybersecurity / RMF | Assess | The system shall identify, scan, triage, and remediate vulnerabilities according to AO-approved timelines with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | IR-4; SC-13 | Test | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-112 | Yes | Yes | In Progress | IMS-016 | A004 | R-112 | Yes
CY-022 | Cybersecurity / RMF | Assess | The system shall collect, correlate, alert, and retain cybersecurity events from boundary, host, application, and repository components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-13; SC-28 | Inspect | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-113 | Yes | Yes | In Progress | IMS-001 | A005 | R-113 | Yes
CY-023 | Cybersecurity / RMF | Assess | The system shall implement cryptographic protection for data in transit and data at rest with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-28; IA-5 | Demonstrate | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-114 | Yes | Yes | In Progress | IMS-002 | A006 | R-114 | Yes
CY-024 | Cybersecurity / RMF | Assess | The system shall maintain a current POA&M for open findings, residual risks, mitigations, owners, and target closure dates with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | IA-5; RA-5 | Analyze | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-115 | Yes | Yes | Not Started | IMS-003 | A007 | R-115 | Yes
CY-025 | Cybersecurity / RMF | Assess | The system shall implement RMF activities, artifacts, and evidence needed to support IATT and ATO decisions with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | RA-5; CA-2 | Test | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-116 | Yes | Yes | In Progress | IMS-004 | A008 | R-116 | Yes
CY-026 | Cybersecurity / RMF | Assess | The system shall apply selected NIST SP 800-53 controls and document implementation details in the System Security Plan with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CA-2; CA-7 | Inspect | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-117 | Yes | Yes | In Progress | IMS-005 | A009 | R-117 | Yes
CY-027 | Cybersecurity / RMF | Assess | The system shall identify, scan, triage, and remediate vulnerabilities according to AO-approved timelines with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CA-7; SI-4 | Demonstrate | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-118 | Yes | Yes | In Progress | IMS-006 | A010 | R-118 | Yes
CY-028 | Cybersecurity / RMF | Assess | The system shall collect, correlate, alert, and retain cybersecurity events from boundary, host, application, and repository components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-4; IR-4 | Analyze | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-119 | Yes | Yes | In Progress | IMS-007 | A011 | R-119 | Yes
CY-029 | Cybersecurity / RMF | Assess | The system shall implement cryptographic protection for data in transit and data at rest with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | IR-4; SC-13 | Test | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-120 | Yes | Yes | Not Started | IMS-008 | A012 | R-120 | Yes
CY-030 | Cybersecurity / RMF | Assess | The system shall maintain a current POA&M for open findings, residual risks, mitigations, owners, and target closure dates with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-13; SC-28 | Inspect | Control implementation evidence is complete, assessment findings are documented, residual risk is captured, and AO review supports the applicable gate. | EV-121 | Yes | Yes | In Progress | IMS-009 | A013 | R-121 | Yes
INT-001 | Interfaces & Interconnections | Implement | The system shall provide controlled interfaces between internal and external networks using approved boundary protection mechanisms with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-7; CA-3 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-122 | Yes | Yes | In Progress | IMS-010 | A014 | R-122 | Yes
INT-002 | Interfaces & Interconnections | Implement | The system shall support bidirectional and unidirectional data exchanges where authorized by interface agreements with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CA-3; AC-4 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-123 | Yes | Yes | In Progress | IMS-011 | A015 | R-123 | Yes
INT-003 | Interfaces & Interconnections | Implement | The system shall document all interconnections in Interface Control Documents and Interconnection Security Agreements with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | AC-4; SC-8 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-124 | Yes | Yes | In Progress | IMS-012 | A016 | R-124 | Yes
INT-004 | Interfaces & Interconnections | Implement | The system shall validate cross-boundary traffic flows against approved ports, protocols, and services with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-8; SC-13 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-125 | Yes | Yes | Not Started | IMS-013 | A017 | R-125 | Yes
INT-005 | Interfaces & Interconnections | Implement | The system shall isolate system boundaries and prevent unauthorized routing or data leakage with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-13; SC-7 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-126 | Yes | Yes | In Progress | IMS-014 | A018 | R-126 | Yes
INT-006 | Interfaces & Interconnections | Implement | The system shall provide controlled interfaces between internal and external networks using approved boundary protection mechanisms with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-7; CA-3 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-127 | Yes | Yes | In Progress | IMS-015 | A001 | R-127 | Yes
INT-007 | Interfaces & Interconnections | Implement | The system shall support bidirectional and unidirectional data exchanges where authorized by interface agreements with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CA-3; AC-4 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-128 | Yes | Yes | In Progress | IMS-016 | A002 | R-128 | Yes
INT-008 | Interfaces & Interconnections | Implement | The system shall document all interconnections in Interface Control Documents and Interconnection Security Agreements with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AC-4; SC-8 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-129 | Yes | Yes | In Progress | IMS-001 | A003 | R-129 | Yes
INT-009 | Interfaces & Interconnections | Implement | The system shall validate cross-boundary traffic flows against approved ports, protocols, and services with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-8; SC-13 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-130 | Yes | Yes | Not Started | IMS-002 | A004 | R-130 | Yes
INT-010 | Interfaces & Interconnections | Implement | The system shall isolate system boundaries and prevent unauthorized routing or data leakage with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-13; SC-7 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-131 | Yes | Yes | In Progress | IMS-003 | A005 | R-131 | Yes
INT-011 | Interfaces & Interconnections | Implement | The system shall provide controlled interfaces between internal and external networks using approved boundary protection mechanisms with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-7; CA-3 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-132 | Yes | Yes | In Progress | IMS-004 | A006 | R-132 | Yes
INT-012 | Interfaces & Interconnections | Implement | The system shall support bidirectional and unidirectional data exchanges where authorized by interface agreements with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CA-3; AC-4 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-133 | Yes | Yes | In Progress | IMS-005 | A007 | R-133 | Yes
INT-013 | Interfaces & Interconnections | Implement | The system shall document all interconnections in Interface Control Documents and Interconnection Security Agreements with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AC-4; SC-8 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-134 | Yes | Yes | In Progress | IMS-006 | A008 | R-134 | Yes
INT-014 | Interfaces & Interconnections | Implement | The system shall validate cross-boundary traffic flows against approved ports, protocols, and services with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-8; SC-13 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-135 | Yes | Yes | Not Started | IMS-007 | A009 | R-135 | Yes
INT-015 | Interfaces & Interconnections | Implement | The system shall isolate system boundaries and prevent unauthorized routing or data leakage with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | SC-13; SC-7 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-136 | Yes | Yes | In Progress | IMS-008 | A010 | R-136 | Yes
INT-016 | Interfaces & Interconnections | Implement | The system shall provide controlled interfaces between internal and external networks using approved boundary protection mechanisms with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-7; CA-3 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-137 | Yes | Yes | In Progress | IMS-009 | A011 | R-137 | Yes
INT-017 | Interfaces & Interconnections | Implement | The system shall support bidirectional and unidirectional data exchanges where authorized by interface agreements with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CA-3; AC-4 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-138 | Yes | Yes | In Progress | IMS-010 | A012 | R-138 | Yes
INT-018 | Interfaces & Interconnections | Implement | The system shall document all interconnections in Interface Control Documents and Interconnection Security Agreements with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | AC-4; SC-8 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-139 | Yes | Yes | In Progress | IMS-011 | A013 | R-139 | Yes
INT-019 | Interfaces & Interconnections | Implement | The system shall validate cross-boundary traffic flows against approved ports, protocols, and services with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-8; SC-13 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-140 | Yes | Yes | Not Started | IMS-012 | A014 | R-140 | Yes
INT-020 | Interfaces & Interconnections | Implement | The system shall isolate system boundaries and prevent unauthorized routing or data leakage with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SC-13; SC-7 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-141 | Yes | Yes | In Progress | IMS-013 | A015 | R-141 | Yes
OPS-001 | Operations & Sustainment | Monitor | The system shall provide administration, monitoring, maintenance, incident response, and configuration management processes for all operational components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AU-6; CM-3 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-142 | Yes | Yes | In Progress | IMS-014 | A016 | R-142 | Yes
OPS-002 | Operations & Sustainment | Monitor | The system shall log user and system activity for audit, troubleshooting, and cybersecurity monitoring with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-3; CM-8 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-143 | Yes | Yes | In Progress | IMS-015 | A017 | R-143 | Yes
OPS-003 | Operations & Sustainment | Monitor | The system shall maintain patching, firmware update, account review, backup, and restoration procedures with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CM-8; CP-10 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-144 | Yes | Yes | In Progress | IMS-016 | A018 | R-144 | Yes
OPS-004 | Operations & Sustainment | Monitor | The system shall support continuous monitoring reporting and periodic authorization reviews with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CP-10; IR-5 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-145 | Yes | Yes | Not Started | IMS-001 | A001 | R-145 | Yes
OPS-005 | Operations & Sustainment | Monitor | The system shall track operational events and cybersecurity milestones in the Integrated Master Schedule with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | IR-5; MA-2 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-146 | Yes | Yes | In Progress | IMS-002 | A002 | R-146 | Yes
OPS-006 | Operations & Sustainment | Monitor | The system shall provide administration, monitoring, maintenance, incident response, and configuration management processes for all operational components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | MA-2; AU-6 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-147 | Yes | Yes | In Progress | IMS-003 | A003 | R-147 | Yes
OPS-007 | Operations & Sustainment | Monitor | The system shall log user and system activity for audit, troubleshooting, and cybersecurity monitoring with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AU-6; CM-3 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-148 | Yes | Yes | In Progress | IMS-004 | A004 | R-148 | Yes
OPS-008 | Operations & Sustainment | Monitor | The system shall maintain patching, firmware update, account review, backup, and restoration procedures with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-3; CM-8 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-149 | Yes | Yes | In Progress | IMS-005 | A005 | R-149 | Yes
OPS-009 | Operations & Sustainment | Monitor | The system shall support continuous monitoring reporting and periodic authorization reviews with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CM-8; CP-10 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-150 | Yes | Yes | Not Started | IMS-006 | A006 | R-150 | Yes
OPS-010 | Operations & Sustainment | Monitor | The system shall track operational events and cybersecurity milestones in the Integrated Master Schedule with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CP-10; IR-5 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-151 | Yes | Yes | In Progress | IMS-007 | A007 | R-151 | Yes
OPS-011 | Operations & Sustainment | Monitor | The system shall provide administration, monitoring, maintenance, incident response, and configuration management processes for all operational components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | IR-5; MA-2 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-152 | Yes | Yes | In Progress | IMS-008 | A008 | R-152 | Yes
OPS-012 | Operations & Sustainment | Monitor | The system shall log user and system activity for audit, troubleshooting, and cybersecurity monitoring with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | MA-2; AU-6 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-153 | Yes | Yes | In Progress | IMS-009 | A009 | R-153 | Yes
OPS-013 | Operations & Sustainment | Monitor | The system shall maintain patching, firmware update, account review, backup, and restoration procedures with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | AU-6; CM-3 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-154 | Yes | Yes | In Progress | IMS-010 | A010 | R-154 | Yes
OPS-014 | Operations & Sustainment | Monitor | The system shall support continuous monitoring reporting and periodic authorization reviews with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-3; CM-8 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-155 | Yes | Yes | Not Started | IMS-011 | A011 | R-155 | Yes
OPS-015 | Operations & Sustainment | Monitor | The system shall track operational events and cybersecurity milestones in the Integrated Master Schedule with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CM-8; CP-10 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-156 | Yes | Yes | In Progress | IMS-012 | A012 | R-156 | Yes
OPS-016 | Operations & Sustainment | Monitor | The system shall provide administration, monitoring, maintenance, incident response, and configuration management processes for all operational components with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CP-10; IR-5 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-157 | Yes | Yes | In Progress | IMS-013 | A013 | R-157 | Yes
OPS-017 | Operations & Sustainment | Monitor | The system shall log user and system activity for audit, troubleshooting, and cybersecurity monitoring with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | IR-5; MA-2 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-158 | Yes | Yes | In Progress | IMS-014 | A014 | R-158 | Yes
OPS-018 | Operations & Sustainment | Monitor | The system shall maintain patching, firmware update, account review, backup, and restoration procedures with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | MA-2; AU-6 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-159 | Yes | Yes | In Progress | IMS-015 | A015 | R-159 | Yes
SW-001 | Software Development & Delivery | Implement | The system shall integrate with the software development environment and software distribution authoritative source with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SA-10; SA-11 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-160 | Yes | Yes | Not Started | IMS-016 | A016 | R-160 | Yes
SW-002 | Software Development & Delivery | Implement | The system shall support software distribution to test equipment, simulators, and approved operational nodes with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SA-11; CM-5 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-161 | Yes | Yes | In Progress | IMS-001 | A017 | R-161 | Yes
SW-003 | Software Development & Delivery | Implement | The system shall support hardware-in-the-loop test integration with repeatable build and test evidence with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CM-5; CM-7 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-162 | Yes | Yes | In Progress | IMS-002 | A018 | R-162 | Yes
SW-004 | Software Development & Delivery | Implement | The system shall maintain software license services needed to support authorized applications with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-7; SI-7 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-163 | Yes | Yes | In Progress | IMS-003 | A001 | R-163 | Yes
SW-005 | Software Development & Delivery | Implement | The system shall ensure software baselines are traceable from source artifact to deployed configuration with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-7; AC-6 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-164 | Yes | Yes | In Progress | IMS-004 | A002 | R-164 | Yes
SW-006 | Software Development & Delivery | Implement | The system shall integrate with the software development environment and software distribution authoritative source with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | AC-6; SA-10 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-165 | No | Yes | Not Started | IMS-005 | A003 | R-165 | Yes
SW-007 | Software Development & Delivery | Implement | The system shall support software distribution to test equipment, simulators, and approved operational nodes with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SA-10; SA-11 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-166 | No | Yes | In Progress | IMS-006 | A004 | R-166 | Yes
SW-008 | Software Development & Delivery | Implement | The system shall support hardware-in-the-loop test integration with repeatable build and test evidence with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SA-11; CM-5 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-167 | No | Yes | In Progress | IMS-007 | A005 | R-167 | Yes
SW-009 | Software Development & Delivery | Implement | The system shall maintain software license services needed to support authorized applications with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CM-5; CM-7 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-168 | No | Yes | In Progress | IMS-008 | A006 | R-168 | Yes
SW-010 | Software Development & Delivery | Implement | The system shall ensure software baselines are traceable from source artifact to deployed configuration with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-7; SI-7 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-169 | No | Yes | In Progress | IMS-009 | A007 | R-169 | Yes
SW-011 | Software Development & Delivery | Implement | The system shall integrate with the software development environment and software distribution authoritative source with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-7; AC-6 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-170 | No | Yes | Not Started | IMS-010 | A008 | R-170 | Yes
SW-012 | Software Development & Delivery | Implement | The system shall support software distribution to test equipment, simulators, and approved operational nodes with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | AC-6; SA-10 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-171 | No | Yes | In Progress | IMS-011 | A009 | R-171 | Yes
SW-013 | Software Development & Delivery | Implement | The system shall support hardware-in-the-loop test integration with repeatable build and test evidence with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SA-10; SA-11 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-172 | No | Yes | In Progress | IMS-012 | A010 | R-172 | Yes
SW-014 | Software Development & Delivery | Implement | The system shall maintain software license services needed to support authorized applications with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SA-11; CM-5 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-173 | No | Yes | In Progress | IMS-013 | A011 | R-173 | Yes
SW-015 | Software Development & Delivery | Implement | The system shall ensure software baselines are traceable from source artifact to deployed configuration with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | CM-5; CM-7 | Demonstrate | Successful demonstrate confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-174 | No | Yes | In Progress | IMS-014 | A012 | R-174 | Yes
SW-016 | Software Development & Delivery | Implement | The system shall integrate with the software development environment and software distribution authoritative source with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | CM-7; SI-7 | Analyze | Successful analyze confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-175 | No | Yes | Not Started | IMS-015 | A013 | R-175 | Yes
SW-017 | Software Development & Delivery | Implement | The system shall support software distribution to test equipment, simulators, and approved operational nodes with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | High | SI-7; AC-6 | Test | Successful test confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-176 | No | Yes | In Progress | IMS-016 | A014 | R-176 | Yes
SW-018 | Software Development & Delivery | Implement | The system shall support hardware-in-the-loop test integration with repeatable build and test evidence with documented configuration, authorization boundary alignment, and traceable evidence for RMF assessment. | Medium | AC-6; SA-10 | Inspect | Successful inspect confirms requirement behavior, interface/configuration records match the approved baseline, and no critical defects remain open. | EV-177 | No | Yes | In Progress | IMS-001 | A015 | R-177 | Yes

## RMF Controls
Control ID | Family | Control Title | Linked Requirements | Implementation Owner | Implementation Status | Evidence Required | IATT Minimum | ATO Minimum | Assessment Status
AC-3 | AC | Access Enforcement |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
AC-4 | AC | Information Flow Enforcement |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
AC-6 | AC | Least Privilege |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
AU-12 | AU | Audit Generation |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
AU-2 | AU | Event Logging |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
AU-6 | AU | Audit Record Review |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
AU-9 | AU | Audit Protection |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
CA-2 | CA | Control Assessments |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
CA-3 | CA | Information Exchange |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
CA-7 | CA | Continuous Monitoring |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
CM-2 | CM | Baseline Configuration |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
CM-3 | CM | Configuration Change Control |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
CM-5 | CM | Access Restrictions for Change |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
CM-6 | CM | Configuration Settings |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
CM-7 | CM | Least Functionality |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
CM-8 | CM | System Component Inventory |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
CP-10 | CP | System Recovery |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
CP-9 | CP | System Backup |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
IA-2 | IA | Identification and Authentication |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
IA-5 | IA | Authenticator Management |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
IR-4 | IR | Incident Handling |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
IR-5 | IR | Incident Monitoring |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
MA-2 | MA | Controlled Maintenance |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
PL-8 | PL | Security Architecture |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
RA-5 | RA | Vulnerability Monitoring and Scanning |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
SA-10 | SA | Developer Configuration Management |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
SA-11 | SA | Developer Testing and Evaluation |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | As Applicable | Yes | Pending Assessment
SC-13 | SC | Cryptographic Protection |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
SC-28 | SC | Protection of Information at Rest |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
SC-45 | SC | System Time Synchronization |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
SC-7 | SC | Boundary Protection |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
SC-8 | SC | Transmission Confidentiality and Integrity |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
SI-10 | SI | Input Validation |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
SI-12 | SI | Information Management and Retention |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
SI-4 | SI | System Monitoring |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment
SI-7 | SI | Software/Firmware Integrity |  | ISSM / Control Owner | In Progress | SSP implementation statement; test evidence; configuration screenshot/log | Yes | Yes | Pending Assessment

## Evidence Tracker
Evidence ID | Linked Req | Linked Control(s) | Artifact Name | Artifact Type | RMF Step | Gate | Owner | Due Date | Status | Repository / Location | Review Notes
EV-001 | FTN-001 | SC-7; SC-8 | FTN-001 Evidence Package | Scan Result | Implement | IATT | Assigned Owner | 2026-05-22 | Not Started | Repository path / EV-001
EV-002 | FTN-002 | SC-8; SC-45 | FTN-002 Evidence Package | STIG Checklist | Implement | IATT | Assigned Owner | 2026-05-29 | Not Started | Repository path / EV-002
EV-003 | FTN-003 | SC-45; AU-2 | FTN-003 Evidence Package | Config Export | Implement | ATO | Assigned Owner | 2026-06-05 | Not Started | Repository path / EV-003
EV-004 | FTN-004 | AU-2; SI-4 | FTN-004 Evidence Package | Test Report | Implement | IATT | Assigned Owner | 2026-06-12 | Not Started | Repository path / EV-004
EV-005 | FTN-005 | SI-4; CM-2 | FTN-005 Evidence Package | Diagram | Implement | IATT | Assigned Owner | 2026-06-19 | Not Started | Repository path / EV-005
EV-006 | FTN-006 | CM-2; SC-7 | FTN-006 Evidence Package | ISA/ICD | Implement | ATO | Assigned Owner | 2026-06-26 | Not Started | Repository path / EV-006
EV-007 | FTN-007 | SC-7; SC-8 | FTN-007 Evidence Package | Policy/Plan | Implement | IATT | Assigned Owner | 2026-07-03 | Not Started | Repository path / EV-007
EV-008 | FTN-008 | SC-8; SC-45 | FTN-008 Evidence Package | SSP Section | Implement | IATT | Assigned Owner | 2026-07-10 | Not Started | Repository path / EV-008
EV-009 | FTN-009 | SC-45; AU-2 | FTN-009 Evidence Package | Scan Result | Implement | ATO | Assigned Owner | 2026-07-17 | Not Started | Repository path / EV-009
EV-010 | FTN-010 | AU-2; SI-4 | FTN-010 Evidence Package | STIG Checklist | Implement | IATT | Assigned Owner | 2026-07-24 | Not Started | Repository path / EV-010
EV-011 | FTN-011 | SI-4; CM-2 | FTN-011 Evidence Package | Config Export | Implement | IATT | Assigned Owner | 2026-07-31 | Not Started | Repository path / EV-011
EV-012 | FTN-012 | CM-2; SC-7 | FTN-012 Evidence Package | Test Report | Implement | ATO | Assigned Owner | 2026-08-07 | Not Started | Repository path / EV-012
EV-013 | FTN-013 | SC-7; SC-8 | FTN-013 Evidence Package | Diagram | Implement | IATT | Assigned Owner | 2026-08-14 | Not Started | Repository path / EV-013
EV-014 | FTN-014 | SC-8; SC-45 | FTN-014 Evidence Package | ISA/ICD | Implement | IATT | Assigned Owner | 2026-08-21 | Not Started | Repository path / EV-014
EV-015 | FTN-015 | SC-45; AU-2 | FTN-015 Evidence Package | Policy/Plan | Implement | ATO | Assigned Owner | 2026-08-28 | Not Started | Repository path / EV-015
EV-016 | FTN-016 | AU-2; SI-4 | FTN-016 Evidence Package | SSP Section | Implement | IATT | Assigned Owner | 2026-09-04 | Not Started | Repository path / EV-016
EV-017 | FTN-017 | SI-4; CM-2 | FTN-017 Evidence Package | Scan Result | Implement | IATT | Assigned Owner | 2026-09-11 | Not Started | Repository path / EV-017
EV-018 | FTN-018 | CM-2; SC-7 | FTN-018 Evidence Package | STIG Checklist | Implement | ATO | Assigned Owner | 2026-09-18 | Not Started | Repository path / EV-018
EV-019 | FTN-019 | SC-7; SC-8 | FTN-019 Evidence Package | Config Export | Implement | IATT | Assigned Owner | 2026-09-25 | Not Started | Repository path / EV-019
EV-020 | FTN-020 | SC-8; SC-45 | FTN-020 Evidence Package | Test Report | Implement | IATT | Assigned Owner | 2026-10-02 | Not Started | Repository path / EV-020
EV-021 | FTN-021 | SC-45; AU-2 | FTN-021 Evidence Package | Diagram | Implement | ATO | Assigned Owner | 2026-10-09 | Not Started | Repository path / EV-021
EV-022 | FTN-022 | AU-2; SI-4 | FTN-022 Evidence Package | ISA/ICD | Implement | IATT | Assigned Owner | 2026-10-16 | Not Started | Repository path / EV-022
EV-023 | FTN-023 | SI-4; CM-2 | FTN-023 Evidence Package | Policy/Plan | Implement | IATT | Assigned Owner | 2026-10-23 | Not Started | Repository path / EV-023
EV-024 | FTN-024 | CM-2; SC-7 | FTN-024 Evidence Package | SSP Section | Implement | ATO | Assigned Owner | 2026-05-15 | Not Started | Repository path / EV-024
EV-025 | FN-001 | CM-2; CM-6 | FN-001 Evidence Package | Scan Result | Implement | IATT | Assigned Owner | 2026-05-22 | Not Started | Repository path / EV-025
EV-026 | FN-002 | CM-6; SC-8 | FN-002 Evidence Package | STIG Checklist | Implement | IATT | Assigned Owner | 2026-05-29 | Not Started | Repository path / EV-026
EV-027 | FN-003 | SC-8; SC-28 | FN-003 Evidence Package | Config Export | Implement | ATO | Assigned Owner | 2026-06-05 | Not Started | Repository path / EV-027
EV-028 | FN-004 | SC-28; SA-11 | FN-004 Evidence Package | Test Report | Implement | IATT | Assigned Owner | 2026-06-12 | Not Started | Repository path / EV-028
EV-029 | FN-005 | SA-11; AC-3 | FN-005 Evidence Package | Diagram | Implement | IATT | Assigned Owner | 2026-06-19 | Not Started | Repository path / EV-029
EV-030 | FN-006 | AC-3; CM-2 | FN-006 Evidence Package | ISA/ICD | Implement | ATO | Assigned Owner | 2026-06-26 | Not Started | Repository path / EV-030
EV-031 | FN-007 | CM-2; CM-6 | FN-007 Evidence Package | Policy/Plan | Implement | IATT | Assigned Owner | 2026-07-03 | Not Started | Repository path / EV-031
EV-032 | FN-008 | CM-6; SC-8 | FN-008 Evidence Package | SSP Section | Implement | IATT | Assigned Owner | 2026-07-10 | Not Started | Repository path / EV-032
EV-033 | FN-009 | SC-8; SC-28 | FN-009 Evidence Package | Scan Result | Implement | ATO | Assigned Owner | 2026-07-17 | Not Started | Repository path / EV-033
EV-034 | FN-010 | SC-28; SA-11 | FN-010 Evidence Package | STIG Checklist | Implement | IATT | Assigned Owner | 2026-07-24 | Not Started | Repository path / EV-034
EV-035 | FN-011 | SA-11; AC-3 | FN-011 Evidence Package | Config Export | Implement | IATT | Assigned Owner | 2026-07-31 | Not Started | Repository path / EV-035
EV-036 | FN-012 | AC-3; CM-2 | FN-012 Evidence Package | Test Report | Implement | ATO | Assigned Owner | 2026-08-07 | Not Started | Repository path / EV-036
EV-037 | FN-013 | CM-2; CM-6 | FN-013 Evidence Package | Diagram | Implement | IATT | Assigned Owner | 2026-08-14 | Not Started | Repository path / EV-037
EV-038 | FN-014 | CM-6; SC-8 | FN-014 Evidence Package | ISA/ICD | Implement | IATT | Assigned Owner | 2026-08-21 | Not Started | Repository path / EV-038
EV-039 | FN-015 | SC-8; SC-28 | FN-015 Evidence Package | Policy/Plan | Implement | ATO | Assigned Owner | 2026-08-28 | Not Started | Repository path / EV-039
EV-040 | FN-016 | SC-28; SA-11 | FN-016 Evidence Package | SSP Section | Implement | IATT | Assigned Owner | 2026-09-04 | Not Started | Repository path / EV-040
EV-041 | FN-017 | SA-11; AC-3 | FN-017 Evidence Package | Scan Result | Implement | IATT | Assigned Owner | 2026-09-11 | Not Started | Repository path / EV-041
EV-042 | FN-018 | AC-3; CM-2 | FN-018 Evidence Package | STIG Checklist | Implement | ATO | Assigned Owner | 2026-09-18 | Not Started | Repository path / EV-042
EV-043 | FN-019 | CM-2; CM-6 | FN-019 Evidence Package | Config Export | Implement | IATT | Assigned Owner | 2026-09-25 | Not Started | Repository path / EV-043
EV-044 | FN-020 | CM-6; SC-8 | FN-020 Evidence Package | Test Report | Implement | IATT | Assigned Owner | 2026-10-02 | Not Started | Repository path / EV-044
EV-045 | FN-021 | SC-8; SC-28 | FN-021 Evidence Package | Diagram | Implement | ATO | Assigned Owner | 2026-10-09 | Not Started | Repository path / EV-045
EV-046 | FN-022 | SC-28; SA-11 | FN-022 Evidence Package | ISA/ICD | Implement | IATT | Assigned Owner | 2026-10-16 | Not Started | Repository path / EV-046
EV-047 | DEE-001 | AC-3; IA-2 | DEE-001 Evidence Package | Policy/Plan | Implement | IATT | Assigned Owner | 2026-10-23 | Not Started | Repository path / EV-047
EV-048 | DEE-002 | IA-2; SC-28 | DEE-002 Evidence Package | SSP Section | Implement | ATO | Assigned Owner | 2026-05-15 | Not Started | Repository path / EV-048
EV-049 | DEE-003 | SC-28; SI-10 | DEE-003 Evidence Package | Scan Result | Implement | IATT | Assigned Owner | 2026-05-22 | Not Started | Repository path / EV-049
EV-050 | DEE-004 | SI-10; AU-12 | DEE-004 Evidence Package | STIG Checklist | Implement | IATT | Assigned Owner | 2026-05-29 | Not Started | Repository path / EV-050
EV-051 | DEE-005 | AU-12; PL-8 | DEE-005 Evidence Package | Config Export | Implement | ATO | Assigned Owner | 2026-06-05 | Not Started | Repository path / EV-051
EV-052 | DEE-006 | PL-8; AC-3 | DEE-006 Evidence Package | Test Report | Implement | ATO | Assigned Owner | 2026-06-12 | Not Started | Repository path / EV-052
EV-053 | DEE-007 | AC-3; IA-2 | DEE-007 Evidence Package | Diagram | Implement | ATO | Assigned Owner | 2026-06-19 | Not Started | Repository path / EV-053
EV-054 | DEE-008 | IA-2; SC-28 | DEE-008 Evidence Package | ISA/ICD | Implement | ATO | Assigned Owner | 2026-06-26 | Not Started | Repository path / EV-054
EV-055 | DEE-009 | SC-28; SI-10 | DEE-009 Evidence Package | Policy/Plan | Implement | ATO | Assigned Owner | 2026-07-03 | Not Started | Repository path / EV-055
EV-056 | DEE-010 | SI-10; AU-12 | DEE-010 Evidence Package | SSP Section | Implement | ATO | Assigned Owner | 2026-07-10 | Not Started | Repository path / EV-056
EV-057 | DEE-011 | AU-12; PL-8 | DEE-011 Evidence Package | Scan Result | Implement | ATO | Assigned Owner | 2026-07-17 | Not Started | Repository path / EV-057
EV-058 | DEE-012 | PL-8; AC-3 | DEE-012 Evidence Package | STIG Checklist | Implement | ATO | Assigned Owner | 2026-07-24 | Not Started | Repository path / EV-058
EV-059 | DEE-013 | AC-3; IA-2 | DEE-013 Evidence Package | Config Export | Implement | ATO | Assigned Owner | 2026-07-31 | Not Started | Repository path / EV-059
EV-060 | DEE-014 | IA-2; SC-28 | DEE-014 Evidence Package | Test Report | Implement | ATO | Assigned Owner | 2026-08-07 | Not Started | Repository path / EV-060
EV-061 | DEE-015 | SC-28; SI-10 | DEE-015 Evidence Package | Diagram | Implement | ATO | Assigned Owner | 2026-08-14 | Not Started | Repository path / EV-061
EV-062 | DEE-016 | SI-10; AU-12 | DEE-016 Evidence Package | ISA/ICD | Implement | ATO | Assigned Owner | 2026-08-21 | Not Started | Repository path / EV-062
EV-063 | DEE-017 | AU-12; PL-8 | DEE-017 Evidence Package | Policy/Plan | Implement | ATO | Assigned Owner | 2026-08-28 | Not Started | Repository path / EV-063
EV-064 | DEE-018 | PL-8; AC-3 | DEE-018 Evidence Package | SSP Section | Implement | ATO | Assigned Owner | 2026-09-04 | Not Started | Repository path / EV-064
EV-065 | DEE-019 | AC-3; IA-2 | DEE-019 Evidence Package | Scan Result | Implement | ATO | Assigned Owner | 2026-09-11 | Not Started | Repository path / EV-065
EV-066 | DEE-020 | IA-2; SC-28 | DEE-020 Evidence Package | STIG Checklist | Implement | ATO | Assigned Owner | 2026-09-18 | Not Started | Repository path / EV-066
EV-067 | DEE-021 | SC-28; SI-10 | DEE-021 Evidence Package | Config Export | Implement | ATO | Assigned Owner | 2026-09-25 | Not Started | Repository path / EV-067
EV-068 | DEE-022 | SI-10; AU-12 | DEE-022 Evidence Package | Test Report | Implement | ATO | Assigned Owner | 2026-10-02 | Not Started | Repository path / EV-068
EV-069 | DEE-023 | AU-12; PL-8 | DEE-023 Evidence Package | Diagram | Implement | ATO | Assigned Owner | 2026-10-09 | Not Started | Repository path / EV-069
EV-070 | DATA-001 | SC-28; SC-8 | DATA-001 Evidence Package | ISA/ICD | Implement | IATT | Assigned Owner | 2026-10-16 | Not Started | Repository path / EV-070
EV-071 | DATA-002 | SC-8; AU-9 | DATA-002 Evidence Package | Policy/Plan | Implement | IATT | Assigned Owner | 2026-10-23 | Not Started | Repository path / EV-071
EV-072 | DATA-003 | AU-9; AC-6 | DATA-003 Evidence Package | SSP Section | Implement | ATO | Assigned Owner | 2026-05-15 | Not Started | Repository path / EV-072
EV-073 | DATA-004 | AC-6; SI-12 | DATA-004 Evidence Package | Scan Result | Implement | IATT | Assigned Owner | 2026-05-22 | Not Started | Repository path / EV-073
EV-074 | DATA-005 | SI-12; CP-9 | DATA-005 Evidence Package | STIG Checklist | Implement | IATT | Assigned Owner | 2026-05-29 | Not Started | Repository path / EV-074
EV-075 | DATA-006 | CP-9; SC-28 | DATA-006 Evidence Package | Config Export | Implement | ATO | Assigned Owner | 2026-06-05 | Not Started | Repository path / EV-075
EV-076 | DATA-007 | SC-28; SC-8 | DATA-007 Evidence Package | Test Report | Implement | ATO | Assigned Owner | 2026-06-12 | Not Started | Repository path / EV-076
EV-077 | DATA-008 | SC-8; AU-9 | DATA-008 Evidence Package | Diagram | Implement | ATO | Assigned Owner | 2026-06-19 | Not Started | Repository path / EV-077
EV-078 | DATA-009 | AU-9; AC-6 | DATA-009 Evidence Package | ISA/ICD | Implement | ATO | Assigned Owner | 2026-06-26 | Not Started | Repository path / EV-078
EV-079 | DATA-010 | AC-6; SI-12 | DATA-010 Evidence Package | Policy/Plan | Implement | ATO | Assigned Owner | 2026-07-03 | Not Started | Repository path / EV-079
EV-080 | DATA-011 | SI-12; CP-9 | DATA-011 Evidence Package | SSP Section | Implement | ATO | Assigned Owner | 2026-07-10 | Not Started | Repository path / EV-080
EV-081 | DATA-012 | CP-9; SC-28 | DATA-012 Evidence Package | Scan Result | Implement | ATO | Assigned Owner | 2026-07-17 | Not Started | Repository path / EV-081
EV-082 | DATA-013 | SC-28; SC-8 | DATA-013 Evidence Package | STIG Checklist | Implement | ATO | Assigned Owner | 2026-07-24 | Not Started | Repository path / EV-082
EV-083 | DATA-014 | SC-8; AU-9 | DATA-014 Evidence Package | Config Export | Implement | ATO | Assigned Owner | 2026-07-31 | Not Started | Repository path / EV-083
EV-084 | DATA-015 | AU-9; AC-6 | DATA-015 Evidence Package | Test Report | Implement | ATO | Assigned Owner | 2026-08-07 | Not Started | Repository path / EV-084
EV-085 | DATA-016 | AC-6; SI-12 | DATA-016 Evidence Package | Diagram | Implement | ATO | Assigned Owner | 2026-08-14 | Not Started | Repository path / EV-085
EV-086 | DATA-017 | SI-12; CP-9 | DATA-017 Evidence Package | ISA/ICD | Implement | ATO | Assigned Owner | 2026-08-21 | Not Started | Repository path / EV-086
EV-087 | DATA-018 | CP-9; SC-28 | DATA-018 Evidence Package | Policy/Plan | Implement | ATO | Assigned Owner | 2026-08-28 | Not Started | Repository path / EV-087
EV-088 | DATA-019 | SC-28; SC-8 | DATA-019 Evidence Package | SSP Section | Implement | ATO | Assigned Owner | 2026-09-04 | Not Started | Repository path / EV-088
EV-089 | DATA-020 | SC-8; AU-9 | DATA-020 Evidence Package | Scan Result | Implement | ATO | Assigned Owner | 2026-09-11 | Not Started | Repository path / EV-089
EV-090 | DATA-021 | AU-9; AC-6 | DATA-021 Evidence Package | STIG Checklist | Implement | ATO | Assigned Owner | 2026-09-18 | Not Started | Repository path / EV-090
EV-091 | DATA-022 | AC-6; SI-12 | DATA-022 Evidence Package | Config Export | Implement | ATO | Assigned Owner | 2026-09-25 | Not Started | Repository path / EV-091
EV-092 | CY-001 | RA-5; CA-2 | CY-001 Evidence Package | Test Report | Assess | IATT | Assigned Owner | 2026-10-02 | Not Started | Repository path / EV-092
EV-093 | CY-002 | CA-2; CA-7 | CY-002 Evidence Package | Diagram | Assess | ATO | Assigned Owner | 2026-10-09 | Not Started | Repository path / EV-093
EV-094 | CY-003 | CA-7; SI-4 | CY-003 Evidence Package | ISA/ICD | Assess | IATT | Assigned Owner | 2026-10-16 | Not Started | Repository path / EV-094
EV-095 | CY-004 | SI-4; IR-4 | CY-004 Evidence Package | Policy/Plan | Assess | IATT | Assigned Owner | 2026-10-23 | Not Started | Repository path / EV-095
EV-096 | CY-005 | IR-4; SC-13 | CY-005 Evidence Package | SSP Section | Assess | ATO | Assigned Owner | 2026-05-15 | Not Started | Repository path / EV-096
EV-097 | CY-006 | SC-13; SC-28 | CY-006 Evidence Package | Scan Result | Assess | IATT | Assigned Owner | 2026-05-22 | Not Started | Repository path / EV-097
EV-098 | CY-007 | SC-28; IA-5 | CY-007 Evidence Package | STIG Checklist | Assess | IATT | Assigned Owner | 2026-05-29 | Not Started | Repository path / EV-098
EV-099 | CY-008 | IA-5; RA-5 | CY-008 Evidence Package | Config Export | Assess | ATO | Assigned Owner | 2026-06-05 | Not Started | Repository path / EV-099
EV-100 | CY-009 | RA-5; CA-2 | CY-009 Evidence Package | Test Report | Assess | IATT | Assigned Owner | 2026-06-12 | Not Started | Repository path / EV-100
EV-101 | CY-010 | CA-2; CA-7 | CY-010 Evidence Package | Diagram | Assess | IATT | Assigned Owner | 2026-06-19 | Not Started | Repository path / EV-101
EV-102 | CY-011 | CA-7; SI-4 | CY-011 Evidence Package | ISA/ICD | Assess | ATO | Assigned Owner | 2026-06-26 | Not Started | Repository path / EV-102
EV-103 | CY-012 | SI-4; IR-4 | CY-012 Evidence Package | Policy/Plan | Assess | IATT | Assigned Owner | 2026-07-03 | Not Started | Repository path / EV-103
EV-104 | CY-013 | IR-4; SC-13 | CY-013 Evidence Package | SSP Section | Assess | IATT | Assigned Owner | 2026-07-10 | Not Started | Repository path / EV-104
EV-105 | CY-014 | SC-13; SC-28 | CY-014 Evidence Package | Scan Result | Assess | ATO | Assigned Owner | 2026-07-17 | Not Started | Repository path / EV-105
EV-106 | CY-015 | SC-28; IA-5 | CY-015 Evidence Package | STIG Checklist | Assess | IATT | Assigned Owner | 2026-07-24 | Not Started | Repository path / EV-106
EV-107 | CY-016 | IA-5; RA-5 | CY-016 Evidence Package | Config Export | Assess | IATT | Assigned Owner | 2026-07-31 | Not Started | Repository path / EV-107
EV-108 | CY-017 | RA-5; CA-2 | CY-017 Evidence Package | Test Report | Assess | ATO | Assigned Owner | 2026-08-07 | Not Started | Repository path / EV-108
EV-109 | CY-018 | CA-2; CA-7 | CY-018 Evidence Package | Diagram | Assess | IATT | Assigned Owner | 2026-08-14 | Not Started | Repository path / EV-109
EV-110 | CY-019 | CA-7; SI-4 | CY-019 Evidence Package | ISA/ICD | Assess | IATT | Assigned Owner | 2026-08-21 | Not Started | Repository path / EV-110
EV-111 | CY-020 | SI-4; IR-4 | CY-020 Evidence Package | Policy/Plan | Assess | ATO | Assigned Owner | 2026-08-28 | Not Started | Repository path / EV-111
EV-112 | CY-021 | IR-4; SC-13 | CY-021 Evidence Package | SSP Section | Assess | IATT | Assigned Owner | 2026-09-04 | Not Started | Repository path / EV-112
EV-113 | CY-022 | SC-13; SC-28 | CY-022 Evidence Package | Scan Result | Assess | IATT | Assigned Owner | 2026-09-11 | Not Started | Repository path / EV-113
EV-114 | CY-023 | SC-28; IA-5 | CY-023 Evidence Package | STIG Checklist | Assess | ATO | Assigned Owner | 2026-09-18 | Not Started | Repository path / EV-114
EV-115 | CY-024 | IA-5; RA-5 | CY-024 Evidence Package | Config Export | Assess | IATT | Assigned Owner | 2026-09-25 | Not Started | Repository path / EV-115
EV-116 | CY-025 | RA-5; CA-2 | CY-025 Evidence Package | Test Report | Assess | IATT | Assigned Owner | 2026-10-02 | Not Started | Repository path / EV-116
EV-117 | CY-026 | CA-2; CA-7 | CY-026 Evidence Package | Diagram | Assess | ATO | Assigned Owner | 2026-10-09 | Not Started | Repository path / EV-117
EV-118 | CY-027 | CA-7; SI-4 | CY-027 Evidence Package | ISA/ICD | Assess | IATT | Assigned Owner | 2026-10-16 | Not Started | Repository path / EV-118
EV-119 | CY-028 | SI-4; IR-4 | CY-028 Evidence Package | Policy/Plan | Assess | IATT | Assigned Owner | 2026-10-23 | Not Started | Repository path / EV-119
EV-120 | CY-029 | IR-4; SC-13 | CY-029 Evidence Package | SSP Section | Assess | ATO | Assigned Owner | 2026-05-15 | Not Started | Repository path / EV-120
EV-121 | CY-030 | SC-13; SC-28 | CY-030 Evidence Package | Scan Result | Assess | IATT | Assigned Owner | 2026-05-22 | Not Started | Repository path / EV-121
EV-122 | INT-001 | SC-7; CA-3 | INT-001 Evidence Package | STIG Checklist | Implement | IATT | Assigned Owner | 2026-05-29 | Not Started | Repository path / EV-122
EV-123 | INT-002 | CA-3; AC-4 | INT-002 Evidence Package | Config Export | Implement | ATO | Assigned Owner | 2026-06-05 | Not Started | Repository path / EV-123
EV-124 | INT-003 | AC-4; SC-8 | INT-003 Evidence Package | Test Report | Implement | IATT | Assigned Owner | 2026-06-12 | Not Started | Repository path / EV-124
EV-125 | INT-004 | SC-8; SC-13 | INT-004 Evidence Package | Diagram | Implement | IATT | Assigned Owner | 2026-06-19 | Not Started | Repository path / EV-125
EV-126 | INT-005 | SC-13; SC-7 | INT-005 Evidence Package | ISA/ICD | Implement | ATO | Assigned Owner | 2026-06-26 | Not Started | Repository path / EV-126
EV-127 | INT-006 | SC-7; CA-3 | INT-006 Evidence Package | Policy/Plan | Implement | IATT | Assigned Owner | 2026-07-03 | Not Started | Repository path / EV-127
EV-128 | INT-007 | CA-3; AC-4 | INT-007 Evidence Package | SSP Section | Implement | IATT | Assigned Owner | 2026-07-10 | Not Started | Repository path / EV-128
EV-129 | INT-008 | AC-4; SC-8 | INT-008 Evidence Package | Scan Result | Implement | ATO | Assigned Owner | 2026-07-17 | Not Started | Repository path / EV-129
EV-130 | INT-009 | SC-8; SC-13 | INT-009 Evidence Package | STIG Checklist | Implement | IATT | Assigned Owner | 2026-07-24 | Not Started | Repository path / EV-130
EV-131 | INT-010 | SC-13; SC-7 | INT-010 Evidence Package | Config Export | Implement | IATT | Assigned Owner | 2026-07-31 | Not Started | Repository path / EV-131
EV-132 | INT-011 | SC-7; CA-3 | INT-011 Evidence Package | Test Report | Implement | ATO | Assigned Owner | 2026-08-07 | Not Started | Repository path / EV-132
EV-133 | INT-012 | CA-3; AC-4 | INT-012 Evidence Package | Diagram | Implement | IATT | Assigned Owner | 2026-08-14 | Not Started | Repository path / EV-133
EV-134 | INT-013 | AC-4; SC-8 | INT-013 Evidence Package | ISA/ICD | Implement | IATT | Assigned Owner | 2026-08-21 | Not Started | Repository path / EV-134
EV-135 | INT-014 | SC-8; SC-13 | INT-014 Evidence Package | Policy/Plan | Implement | ATO | Assigned Owner | 2026-08-28 | Not Started | Repository path / EV-135
EV-136 | INT-015 | SC-13; SC-7 | INT-015 Evidence Package | SSP Section | Implement | IATT | Assigned Owner | 2026-09-04 | Not Started | Repository path / EV-136
EV-137 | INT-016 | SC-7; CA-3 | INT-016 Evidence Package | Scan Result | Implement | IATT | Assigned Owner | 2026-09-11 | Not Started | Repository path / EV-137
EV-138 | INT-017 | CA-3; AC-4 | INT-017 Evidence Package | STIG Checklist | Implement | ATO | Assigned Owner | 2026-09-18 | Not Started | Repository path / EV-138
EV-139 | INT-018 | AC-4; SC-8 | INT-018 Evidence Package | Config Export | Implement | IATT | Assigned Owner | 2026-09-25 | Not Started | Repository path / EV-139
EV-140 | INT-019 | SC-8; SC-13 | INT-019 Evidence Package | Test Report | Implement | IATT | Assigned Owner | 2026-10-02 | Not Started | Repository path / EV-140
EV-141 | INT-020 | SC-13; SC-7 | INT-020 Evidence Package | Diagram | Implement | ATO | Assigned Owner | 2026-10-09 | Not Started | Repository path / EV-141
EV-142 | OPS-001 | AU-6; CM-3 | OPS-001 Evidence Package | ISA/ICD | Monitor | IATT | Assigned Owner | 2026-10-16 | Not Started | Repository path / EV-142
EV-143 | OPS-002 | CM-3; CM-8 | OPS-002 Evidence Package | Policy/Plan | Monitor | IATT | Assigned Owner | 2026-10-23 | Not Started | Repository path / EV-143
EV-144 | OPS-003 | CM-8; CP-10 | OPS-003 Evidence Package | SSP Section | Monitor | ATO | Assigned Owner | 2026-05-15 | Not Started | Repository path / EV-144
EV-145 | OPS-004 | CP-10; IR-5 | OPS-004 Evidence Package | Scan Result | Monitor | IATT | Assigned Owner | 2026-05-22 | Not Started | Repository path / EV-145
EV-146 | OPS-005 | IR-5; MA-2 | OPS-005 Evidence Package | STIG Checklist | Monitor | IATT | Assigned Owner | 2026-05-29 | Not Started | Repository path / EV-146
EV-147 | OPS-006 | MA-2; AU-6 | OPS-006 Evidence Package | Config Export | Monitor | ATO | Assigned Owner | 2026-06-05 | Not Started | Repository path / EV-147
EV-148 | OPS-007 | AU-6; CM-3 | OPS-007 Evidence Package | Test Report | Monitor | IATT | Assigned Owner | 2026-06-12 | Not Started | Repository path / EV-148
EV-149 | OPS-008 | CM-3; CM-8 | OPS-008 Evidence Package | Diagram | Monitor | IATT | Assigned Owner | 2026-06-19 | Not Started | Repository path / EV-149
EV-150 | OPS-009 | CM-8; CP-10 | OPS-009 Evidence Package | ISA/ICD | Monitor | ATO | Assigned Owner | 2026-06-26 | Not Started | Repository path / EV-150
EV-151 | OPS-010 | CP-10; IR-5 | OPS-010 Evidence Package | Policy/Plan | Monitor | IATT | Assigned Owner | 2026-07-03 | Not Started | Repository path / EV-151
EV-152 | OPS-011 | IR-5; MA-2 | OPS-011 Evidence Package | SSP Section | Monitor | IATT | Assigned Owner | 2026-07-10 | Not Started | Repository path / EV-152
EV-153 | OPS-012 | MA-2; AU-6 | OPS-012 Evidence Package | Scan Result | Monitor | ATO | Assigned Owner | 2026-07-17 | Not Started | Repository path / EV-153
EV-154 | OPS-013 | AU-6; CM-3 | OPS-013 Evidence Package | STIG Checklist | Monitor | IATT | Assigned Owner | 2026-07-24 | Not Started | Repository path / EV-154
EV-155 | OPS-014 | CM-3; CM-8 | OPS-014 Evidence Package | Config Export | Monitor | IATT | Assigned Owner | 2026-07-31 | Not Started | Repository path / EV-155
EV-156 | OPS-015 | CM-8; CP-10 | OPS-015 Evidence Package | Test Report | Monitor | ATO | Assigned Owner | 2026-08-07 | Not Started | Repository path / EV-156
EV-157 | OPS-016 | CP-10; IR-5 | OPS-016 Evidence Package | Diagram | Monitor | IATT | Assigned Owner | 2026-08-14 | Not Started | Repository path / EV-157
EV-158 | OPS-017 | IR-5; MA-2 | OPS-017 Evidence Package | ISA/ICD | Monitor | IATT | Assigned Owner | 2026-08-21 | Not Started | Repository path / EV-158
EV-159 | OPS-018 | MA-2; AU-6 | OPS-018 Evidence Package | Policy/Plan | Monitor | ATO | Assigned Owner | 2026-08-28 | Not Started | Repository path / EV-159
EV-160 | SW-001 | SA-10; SA-11 | SW-001 Evidence Package | SSP Section | Implement | IATT | Assigned Owner | 2026-09-04 | Not Started | Repository path / EV-160
EV-161 | SW-002 | SA-11; CM-5 | SW-002 Evidence Package | Scan Result | Implement | IATT | Assigned Owner | 2026-09-11 | Not Started | Repository path / EV-161
EV-162 | SW-003 | CM-5; CM-7 | SW-003 Evidence Package | STIG Checklist | Implement | ATO | Assigned Owner | 2026-09-18 | Not Started | Repository path / EV-162
EV-163 | SW-004 | CM-7; SI-7 | SW-004 Evidence Package | Config Export | Implement | IATT | Assigned Owner | 2026-09-25 | Not Started | Repository path / EV-163
EV-164 | SW-005 | SI-7; AC-6 | SW-005 Evidence Package | Test Report | Implement | IATT | Assigned Owner | 2026-10-02 | Not Started | Repository path / EV-164
EV-165 | SW-006 | AC-6; SA-10 | SW-006 Evidence Package | Diagram | Implement | ATO | Assigned Owner | 2026-10-09 | Not Started | Repository path / EV-165
EV-166 | SW-007 | SA-10; SA-11 | SW-007 Evidence Package | ISA/ICD | Implement | ATO | Assigned Owner | 2026-10-16 | Not Started | Repository path / EV-166
EV-167 | SW-008 | SA-11; CM-5 | SW-008 Evidence Package | Policy/Plan | Implement | ATO | Assigned Owner | 2026-10-23 | Not Started | Repository path / EV-167
EV-168 | SW-009 | CM-5; CM-7 | SW-009 Evidence Package | SSP Section | Implement | ATO | Assigned Owner | 2026-05-15 | Not Started | Repository path / EV-168
EV-169 | SW-010 | CM-7; SI-7 | SW-010 Evidence Package | Scan Result | Implement | ATO | Assigned Owner | 2026-05-22 | Not Started | Repository path / EV-169
EV-170 | SW-011 | SI-7; AC-6 | SW-011 Evidence Package | STIG Checklist | Implement | ATO | Assigned Owner | 2026-05-29 | Not Started | Repository path / EV-170
EV-171 | SW-012 | AC-6; SA-10 | SW-012 Evidence Package | Config Export | Implement | ATO | Assigned Owner | 2026-06-05 | Not Started | Repository path / EV-171
EV-172 | SW-013 | SA-10; SA-11 | SW-013 Evidence Package | Test Report | Implement | ATO | Assigned Owner | 2026-06-12 | Not Started | Repository path / EV-172
EV-173 | SW-014 | SA-11; CM-5 | SW-014 Evidence Package | Diagram | Implement | ATO | Assigned Owner | 2026-06-19 | Not Started | Repository path / EV-173
EV-174 | SW-015 | CM-5; CM-7 | SW-015 Evidence Package | ISA/ICD | Implement | ATO | Assigned Owner | 2026-06-26 | Not Started | Repository path / EV-174
EV-175 | SW-016 | CM-7; SI-7 | SW-016 Evidence Package | Policy/Plan | Implement | ATO | Assigned Owner | 2026-07-03 | Not Started | Repository path / EV-175
EV-176 | SW-017 | SI-7; AC-6 | SW-017 Evidence Package | SSP Section | Implement | ATO | Assigned Owner | 2026-07-10 | Not Started | Repository path / EV-176
EV-177 | SW-018 | AC-6; SA-10 | SW-018 Evidence Package | Scan Result | Implement | ATO | Assigned Owner | 2026-07-17 | Not Started | Repository path / EV-177

## POAM Automation
POA&M ID | Linked Req | Control ID | Weakness / Finding | Severity | Source | Owner | Open Date | Target Closure | Days Open | Status | Residual Risk | IATT Blocker | ATO Blocker
POAM-001 | FTN-001 | SC-7 | Evidence or control implementation gap for FTN-001 | High | Vulnerability Scan | Action Owner | 2026-05-02 | 2026-06-01 | 2 | Open | High | No | Yes
POAM-002 | FTN-002 | SC-8 | Evidence or control implementation gap for FTN-002 | Medium | STIG Review | Action Owner | 2026-05-03 | 2026-07-02 | 1 | Open | Medium | No | No
POAM-003 | FTN-003 | SC-45 | Evidence or control implementation gap for FTN-003 | Low | Design Review | Action Owner | 2026-05-04 | 2026-08-02 | 0 | Open | Medium | No | No
POAM-004 | FTN-004 | AU-2 | Evidence or control implementation gap for FTN-004 | Critical | Test Event | Action Owner | 2026-05-05 | 2026-05-20 | -1 | Open | High | Yes | Yes
POAM-005 | FTN-005 | SI-4 | Evidence or control implementation gap for FTN-005 | High | Assessment | Action Owner | 2026-05-06 | 2026-06-05 | -2 | Open | High | No | Yes
POAM-006 | FTN-006 | CM-2 | Evidence or control implementation gap for FTN-006 | Medium | Vulnerability Scan | Action Owner | 2026-05-07 | 2026-07-06 | -3 | Mitigated | Low | No | No
POAM-007 | FTN-007 | SC-7 | Evidence or control implementation gap for FTN-007 | Low | STIG Review | Action Owner | 2026-05-08 | 2026-08-06 | -4 | Open | Medium | No | No
POAM-008 | FTN-008 | SC-8 | Evidence or control implementation gap for FTN-008 | Critical | Design Review | Action Owner | 2026-05-09 | 2026-05-24 | -5 | Open | High | Yes | Yes
POAM-009 | FTN-009 | SC-45 | Evidence or control implementation gap for FTN-009 | High | Test Event | Action Owner | 2026-05-10 | 2026-06-09 | -6 | Open | High | No | Yes
POAM-010 | FTN-010 | AU-2 | Evidence or control implementation gap for FTN-010 | Medium | Assessment | Action Owner | 2026-05-11 | 2026-07-10 | -7 | Open | Medium | No | No
POAM-011 | FTN-011 | SI-4 | Evidence or control implementation gap for FTN-011 | Low | Vulnerability Scan | Action Owner | 2026-05-12 | 2026-08-10 | -8 | Open | Medium | No | No
POAM-012 | FTN-012 | CM-2 | Evidence or control implementation gap for FTN-012 | Critical | STIG Review | Action Owner | 2026-05-13 | 2026-05-28 | -9 | Mitigated | Low | Yes | Yes
POAM-013 | FTN-013 | SC-7 | Evidence or control implementation gap for FTN-013 | High | Design Review | Action Owner | 2026-05-14 | 2026-06-13 | -10 | Open | High | No | Yes
POAM-014 | FTN-014 | SC-8 | Evidence or control implementation gap for FTN-014 | Medium | Test Event | Action Owner | 2026-05-15 | 2026-07-14 | -11 | Open | Medium | No | No
POAM-015 | FTN-015 | SC-45 | Evidence or control implementation gap for FTN-015 | Low | Assessment | Action Owner | 2026-05-16 | 2026-08-14 | -12 | Open | Medium | No | No
POAM-016 | FTN-016 | AU-2 | Evidence or control implementation gap for FTN-016 | Critical | Vulnerability Scan | Action Owner | 2026-05-17 | 2026-06-01 | -13 | Open | High | Yes | Yes
POAM-017 | FTN-017 | SI-4 | Evidence or control implementation gap for FTN-017 | High | STIG Review | Action Owner | 2026-05-18 | 2026-06-17 | -14 | Open | High | No | Yes
POAM-018 | FTN-018 | CM-2 | Evidence or control implementation gap for FTN-018 | Medium | Design Review | Action Owner | 2026-05-19 | 2026-07-18 | -15 | Mitigated | Low | No | No
POAM-019 | FTN-019 | SC-7 | Evidence or control implementation gap for FTN-019 | Low | Test Event | Action Owner | 2026-05-20 | 2026-08-18 | -16 | Open | Medium | No | No
POAM-020 | FTN-020 | SC-8 | Evidence or control implementation gap for FTN-020 | Critical | Assessment | Action Owner | 2026-05-21 | 2026-06-05 | -17 | Open | High | Yes | Yes
POAM-021 | FTN-021 | SC-45 | Evidence or control implementation gap for FTN-021 | High | Vulnerability Scan | Action Owner | 2026-05-22 | 2026-06-21 | -18 | Open | High | No | Yes
POAM-022 | FTN-022 | AU-2 | Evidence or control implementation gap for FTN-022 | Medium | STIG Review | Action Owner | 2026-05-23 | 2026-07-22 | -19 | Open | Medium | No | No
POAM-023 | FTN-023 | SI-4 | Evidence or control implementation gap for FTN-023 | Low | Design Review | Action Owner | 2026-05-24 | 2026-08-22 | -20 | Open | Medium | No | No
POAM-024 | FTN-024 | CM-2 | Evidence or control implementation gap for FTN-024 | Critical | Test Event | Action Owner | 2026-05-25 | 2026-06-09 | -21 | Mitigated | Low | Yes | Yes
POAM-025 | FN-001 | CM-2 | Evidence or control implementation gap for FN-001 | High | Assessment | Action Owner | 2026-05-26 | 2026-06-25 | -22 | Open | High | No | Yes
POAM-026 | FN-002 | CM-6 | Evidence or control implementation gap for FN-002 | Medium | Vulnerability Scan | Action Owner | 2026-05-27 | 2026-07-26 | -23 | Open | Medium | No | No
POAM-027 | FN-003 | SC-8 | Evidence or control implementation gap for FN-003 | Low | STIG Review | Action Owner | 2026-05-28 | 2026-08-26 | -24 | Open | Medium | No | No
POAM-028 | FN-004 | SC-28 | Evidence or control implementation gap for FN-004 | Critical | Design Review | Action Owner | 2026-05-29 | 2026-06-13 | -25 | Open | High | Yes | Yes
POAM-029 | FN-005 | SA-11 | Evidence or control implementation gap for FN-005 | High | Test Event | Action Owner | 2026-05-30 | 2026-06-29 | -26 | Open | High | No | Yes
POAM-030 | FN-006 | AC-3 | Evidence or control implementation gap for FN-006 | Medium | Assessment | Action Owner | 2026-05-01 | 2026-06-30 | 3 | Mitigated | Low | No | No
POAM-031 | FN-007 | CM-2 | Evidence or control implementation gap for FN-007 | Low | Vulnerability Scan | Action Owner | 2026-05-02 | 2026-07-31 | 2 | Open | Medium | No | No
POAM-032 | FN-008 | CM-6 | Evidence or control implementation gap for FN-008 | Critical | STIG Review | Action Owner | 2026-05-03 | 2026-05-18 | 1 | Open | High | Yes | Yes
POAM-033 | FN-009 | SC-8 | Evidence or control implementation gap for FN-009 | High | Design Review | Action Owner | 2026-05-04 | 2026-06-03 | 0 | Open | High | No | Yes
POAM-034 | FN-010 | SC-28 | Evidence or control implementation gap for FN-010 | Medium | Test Event | Action Owner | 2026-05-05 | 2026-07-04 | -1 | Open | Medium | No | No
POAM-035 | FN-011 | SA-11 | Evidence or control implementation gap for FN-011 | Low | Assessment | Action Owner | 2026-05-06 | 2026-08-04 | -2 | Open | Medium | No | No
POAM-036 | FN-012 | AC-3 | Evidence or control implementation gap for FN-012 | Critical | Vulnerability Scan | Action Owner | 2026-05-07 | 2026-05-22 | -3 | Mitigated | Low | Yes | Yes
POAM-037 | FN-013 | CM-2 | Evidence or control implementation gap for FN-013 | High | STIG Review | Action Owner | 2026-05-08 | 2026-06-07 | -4 | Open | High | No | Yes
POAM-038 | FN-014 | CM-6 | Evidence or control implementation gap for FN-014 | Medium | Design Review | Action Owner | 2026-05-09 | 2026-07-08 | -5 | Open | Medium | No | No
POAM-039 | FN-015 | SC-8 | Evidence or control implementation gap for FN-015 | Low | Test Event | Action Owner | 2026-05-10 | 2026-08-08 | -6 | Open | Medium | No | No
POAM-040 | FN-016 | SC-28 | Evidence or control implementation gap for FN-016 | Critical | Assessment | Action Owner | 2026-05-11 | 2026-05-26 | -7 | Open | High | Yes | Yes
POAM-041 | FN-017 | SA-11 | Evidence or control implementation gap for FN-017 | High | Vulnerability Scan | Action Owner | 2026-05-12 | 2026-06-11 | -8 | Open | High | No | Yes
POAM-042 | FN-018 | AC-3 | Evidence or control implementation gap for FN-018 | Medium | STIG Review | Action Owner | 2026-05-13 | 2026-07-12 | -9 | Mitigated | Low | No | No
POAM-043 | FN-019 | CM-2 | Evidence or control implementation gap for FN-019 | Low | Design Review | Action Owner | 2026-05-14 | 2026-08-12 | -10 | Open | Medium | No | No
POAM-044 | FN-020 | CM-6 | Evidence or control implementation gap for FN-020 | Critical | Test Event | Action Owner | 2026-05-15 | 2026-05-30 | -11 | Open | High | Yes | Yes
POAM-045 | FN-021 | SC-8 | Evidence or control implementation gap for FN-021 | High | Assessment | Action Owner | 2026-05-16 | 2026-06-15 | -12 | Open | High | No | Yes
POAM-046 | FN-022 | SC-28 | Evidence or control implementation gap for FN-022 | Medium | Vulnerability Scan | Action Owner | 2026-05-17 | 2026-07-16 | -13 | Open | Medium | No | No
POAM-047 | DEE-001 | AC-3 | Evidence or control implementation gap for DEE-001 | Low | STIG Review | Action Owner | 2026-05-18 | 2026-08-16 | -14 | Open | Medium | No | No
POAM-048 | DEE-002 | IA-2 | Evidence or control implementation gap for DEE-002 | Critical | Design Review | Action Owner | 2026-05-19 | 2026-06-03 | -15 | Mitigated | Low | Yes | Yes
POAM-049 | DEE-003 | SC-28 | Evidence or control implementation gap for DEE-003 | High | Test Event | Action Owner | 2026-05-20 | 2026-06-19 | -16 | Open | High | No | Yes
POAM-050 | DEE-004 | SI-10 | Evidence or control implementation gap for DEE-004 | Medium | Assessment | Action Owner | 2026-05-21 | 2026-07-20 | -17 | Open | Medium | No | No
POAM-051 | DEE-005 | AU-12 | Evidence or control implementation gap for DEE-005 | Low | Vulnerability Scan | Action Owner | 2026-05-22 | 2026-08-20 | -18 | Open | Medium | No | No
POAM-052 | DEE-006 | PL-8 | Evidence or control implementation gap for DEE-006 | Critical | STIG Review | Action Owner | 2026-05-23 | 2026-06-07 | -19 | Open | High | Yes | Yes
POAM-053 | DEE-007 | AC-3 | Evidence or control implementation gap for DEE-007 | High | Design Review | Action Owner | 2026-05-24 | 2026-06-23 | -20 | Open | High | No | Yes
POAM-054 | DEE-008 | IA-2 | Evidence or control implementation gap for DEE-008 | Medium | Test Event | Action Owner | 2026-05-25 | 2026-07-24 | -21 | Mitigated | Low | No | No
POAM-055 | DEE-009 | SC-28 | Evidence or control implementation gap for DEE-009 | Low | Assessment | Action Owner | 2026-05-26 | 2026-08-24 | -22 | Open | Medium | No | No
POAM-056 | DEE-010 | SI-10 | Evidence or control implementation gap for DEE-010 | Critical | Vulnerability Scan | Action Owner | 2026-05-27 | 2026-06-11 | -23 | Open | High | Yes | Yes
POAM-057 | DEE-011 | AU-12 | Evidence or control implementation gap for DEE-011 | High | STIG Review | Action Owner | 2026-05-28 | 2026-06-27 | -24 | Open | High | No | Yes
POAM-058 | DEE-012 | PL-8 | Evidence or control implementation gap for DEE-012 | Medium | Design Review | Action Owner | 2026-05-29 | 2026-07-28 | -25 | Open | Medium | No | No
POAM-059 | DEE-013 | AC-3 | Evidence or control implementation gap for DEE-013 | Low | Test Event | Action Owner | 2026-05-30 | 2026-08-28 | -26 | Open | Medium | No | No
POAM-060 | DEE-014 | IA-2 | Evidence or control implementation gap for DEE-014 | Critical | Assessment | Action Owner | 2026-05-01 | 2026-05-16 | 3 | Mitigated | Low | Yes | Yes
POAM-061 | DEE-015 | SC-28 | Evidence or control implementation gap for DEE-015 | High | Vulnerability Scan | Action Owner | 2026-05-02 | 2026-06-01 | 2 | Open | High | No | Yes
POAM-062 | DEE-016 | SI-10 | Evidence or control implementation gap for DEE-016 | Medium | STIG Review | Action Owner | 2026-05-03 | 2026-07-02 | 1 | Open | Medium | No | No
POAM-063 | DEE-017 | AU-12 | Evidence or control implementation gap for DEE-017 | Low | Design Review | Action Owner | 2026-05-04 | 2026-08-02 | 0 | Open | Medium | No | No
POAM-064 | DEE-018 | PL-8 | Evidence or control implementation gap for DEE-018 | Critical | Test Event | Action Owner | 2026-05-05 | 2026-05-20 | -1 | Open | High | Yes | Yes
POAM-065 | DEE-019 | AC-3 | Evidence or control implementation gap for DEE-019 | High | Assessment | Action Owner | 2026-05-06 | 2026-06-05 | -2 | Open | High | No | Yes
POAM-066 | DEE-020 | IA-2 | Evidence or control implementation gap for DEE-020 | Medium | Vulnerability Scan | Action Owner | 2026-05-07 | 2026-07-06 | -3 | Mitigated | Low | No | No
POAM-067 | DEE-021 | SC-28 | Evidence or control implementation gap for DEE-021 | Low | STIG Review | Action Owner | 2026-05-08 | 2026-08-06 | -4 | Open | Medium | No | No
POAM-068 | DEE-022 | SI-10 | Evidence or control implementation gap for DEE-022 | Critical | Design Review | Action Owner | 2026-05-09 | 2026-05-24 | -5 | Open | High | Yes | Yes
POAM-069 | DEE-023 | AU-12 | Evidence or control implementation gap for DEE-023 | High | Test Event | Action Owner | 2026-05-10 | 2026-06-09 | -6 | Open | High | No | Yes
POAM-070 | DATA-001 | SC-28 | Evidence or control implementation gap for DATA-001 | Medium | Assessment | Action Owner | 2026-05-11 | 2026-07-10 | -7 | Open | Medium | No | No
POAM-071 | DATA-002 | SC-8 | Evidence or control implementation gap for DATA-002 | Low | Vulnerability Scan | Action Owner | 2026-05-12 | 2026-08-10 | -8 | Open | Medium | No | No
POAM-072 | DATA-003 | AU-9 | Evidence or control implementation gap for DATA-003 | Critical | STIG Review | Action Owner | 2026-05-13 | 2026-05-28 | -9 | Mitigated | Low | Yes | Yes
POAM-073 | DATA-004 | AC-6 | Evidence or control implementation gap for DATA-004 | High | Design Review | Action Owner | 2026-05-14 | 2026-06-13 | -10 | Open | High | No | Yes
POAM-074 | DATA-005 | SI-12 | Evidence or control implementation gap for DATA-005 | Medium | Test Event | Action Owner | 2026-05-15 | 2026-07-14 | -11 | Open | Medium | No | No
POAM-075 | DATA-006 | CP-9 | Evidence or control implementation gap for DATA-006 | Low | Assessment | Action Owner | 2026-05-16 | 2026-08-14 | -12 | Open | Medium | No | No
POAM-076 | DATA-007 | SC-28 | Evidence or control implementation gap for DATA-007 | Critical | Vulnerability Scan | Action Owner | 2026-05-17 | 2026-06-01 | -13 | Open | High | Yes | Yes
POAM-077 | DATA-008 | SC-8 | Evidence or control implementation gap for DATA-008 | High | STIG Review | Action Owner | 2026-05-18 | 2026-06-17 | -14 | Open | High | No | Yes
POAM-078 | DATA-009 | AU-9 | Evidence or control implementation gap for DATA-009 | Medium | Design Review | Action Owner | 2026-05-19 | 2026-07-18 | -15 | Mitigated | Low | No | No
POAM-079 | DATA-010 | AC-6 | Evidence or control implementation gap for DATA-010 | Low | Test Event | Action Owner | 2026-05-20 | 2026-08-18 | -16 | Open | Medium | No | No
POAM-080 | DATA-011 | SI-12 | Evidence or control implementation gap for DATA-011 | Critical | Assessment | Action Owner | 2026-05-21 | 2026-06-05 | -17 | Open | High | Yes | Yes
POAM-081 | DATA-012 | CP-9 | Evidence or control implementation gap for DATA-012 | High | Vulnerability Scan | Action Owner | 2026-05-22 | 2026-06-21 | -18 | Open | High | No | Yes
POAM-082 | DATA-013 | SC-28 | Evidence or control implementation gap for DATA-013 | Medium | STIG Review | Action Owner | 2026-05-23 | 2026-07-22 | -19 | Open | Medium | No | No
POAM-083 | DATA-014 | SC-8 | Evidence or control implementation gap for DATA-014 | Low | Design Review | Action Owner | 2026-05-24 | 2026-08-22 | -20 | Open | Medium | No | No
POAM-084 | DATA-015 | AU-9 | Evidence or control implementation gap for DATA-015 | Critical | Test Event | Action Owner | 2026-05-25 | 2026-06-09 | -21 | Mitigated | Low | Yes | Yes
POAM-085 | DATA-016 | AC-6 | Evidence or control implementation gap for DATA-016 | High | Assessment | Action Owner | 2026-05-26 | 2026-06-25 | -22 | Open | High | No | Yes
POAM-086 | DATA-017 | SI-12 | Evidence or control implementation gap for DATA-017 | Medium | Vulnerability Scan | Action Owner | 2026-05-27 | 2026-07-26 | -23 | Open | Medium | No | No
POAM-087 | DATA-018 | CP-9 | Evidence or control implementation gap for DATA-018 | Low | STIG Review | Action Owner | 2026-05-28 | 2026-08-26 | -24 | Open | Medium | No | No
POAM-088 | DATA-019 | SC-28 | Evidence or control implementation gap for DATA-019 | Critical | Design Review | Action Owner | 2026-05-29 | 2026-06-13 | -25 | Open | High | Yes | Yes
POAM-089 | DATA-020 | SC-8 | Evidence or control implementation gap for DATA-020 | High | Test Event | Action Owner | 2026-05-30 | 2026-06-29 | -26 | Open | High | No | Yes
POAM-090 | DATA-021 | AU-9 | Evidence or control implementation gap for DATA-021 | Medium | Assessment | Action Owner | 2026-05-01 | 2026-06-30 | 3 | Mitigated | Low | No | No
POAM-091 | DATA-022 | AC-6 | Evidence or control implementation gap for DATA-022 | Low | Vulnerability Scan | Action Owner | 2026-05-02 | 2026-07-31 | 2 | Open | Medium | No | No
POAM-092 | CY-001 | RA-5 | Evidence or control implementation gap for CY-001 | Critical | STIG Review | Action Owner | 2026-05-03 | 2026-05-18 | 1 | Open | High | Yes | Yes
POAM-093 | CY-002 | CA-2 | Evidence or control implementation gap for CY-002 | High | Design Review | Action Owner | 2026-05-04 | 2026-06-03 | 0 | Open | High | No | Yes
POAM-094 | CY-003 | CA-7 | Evidence or control implementation gap for CY-003 | Medium | Test Event | Action Owner | 2026-05-05 | 2026-07-04 | -1 | Open | Medium | No | No
POAM-095 | CY-004 | SI-4 | Evidence or control implementation gap for CY-004 | Low | Assessment | Action Owner | 2026-05-06 | 2026-08-04 | -2 | Open | Medium | No | No
POAM-096 | CY-005 | IR-4 | Evidence or control implementation gap for CY-005 | Critical | Vulnerability Scan | Action Owner | 2026-05-07 | 2026-05-22 | -3 | Mitigated | Low | Yes | Yes
POAM-097 | CY-006 | SC-13 | Evidence or control implementation gap for CY-006 | High | STIG Review | Action Owner | 2026-05-08 | 2026-06-07 | -4 | Open | High | No | Yes
POAM-098 | CY-007 | SC-28 | Evidence or control implementation gap for CY-007 | Medium | Design Review | Action Owner | 2026-05-09 | 2026-07-08 | -5 | Open | Medium | No | No
POAM-099 | CY-008 | IA-5 | Evidence or control implementation gap for CY-008 | Low | Test Event | Action Owner | 2026-05-10 | 2026-08-08 | -6 | Open | Medium | No | No
POAM-100 | CY-009 | RA-5 | Evidence or control implementation gap for CY-009 | Critical | Assessment | Action Owner | 2026-05-11 | 2026-05-26 | -7 | Open | High | Yes | Yes
POAM-101 | CY-010 | CA-2 | Evidence or control implementation gap for CY-010 | High | Vulnerability Scan | Action Owner | 2026-05-12 | 2026-06-11 | -8 | Open | High | No | Yes
POAM-102 | CY-011 | CA-7 | Evidence or control implementation gap for CY-011 | Medium | STIG Review | Action Owner | 2026-05-13 | 2026-07-12 | -9 | Mitigated | Low | No | No
POAM-103 | CY-012 | SI-4 | Evidence or control implementation gap for CY-012 | Low | Design Review | Action Owner | 2026-05-14 | 2026-08-12 | -10 | Open | Medium | No | No
POAM-104 | CY-013 | IR-4 | Evidence or control implementation gap for CY-013 | Critical | Test Event | Action Owner | 2026-05-15 | 2026-05-30 | -11 | Open | High | Yes | Yes
POAM-105 | CY-014 | SC-13 | Evidence or control implementation gap for CY-014 | High | Assessment | Action Owner | 2026-05-16 | 2026-06-15 | -12 | Open | High | No | Yes
POAM-106 | CY-015 | SC-28 | Evidence or control implementation gap for CY-015 | Medium | Vulnerability Scan | Action Owner | 2026-05-17 | 2026-07-16 | -13 | Open | Medium | No | No
POAM-107 | CY-016 | IA-5 | Evidence or control implementation gap for CY-016 | Low | STIG Review | Action Owner | 2026-05-18 | 2026-08-16 | -14 | Open | Medium | No | No
POAM-108 | CY-017 | RA-5 | Evidence or control implementation gap for CY-017 | Critical | Design Review | Action Owner | 2026-05-19 | 2026-06-03 | -15 | Mitigated | Low | Yes | Yes
POAM-109 | CY-018 | CA-2 | Evidence or control implementation gap for CY-018 | High | Test Event | Action Owner | 2026-05-20 | 2026-06-19 | -16 | Open | High | No | Yes
POAM-110 | CY-019 | CA-7 | Evidence or control implementation gap for CY-019 | Medium | Assessment | Action Owner | 2026-05-21 | 2026-07-20 | -17 | Open | Medium | No | No
POAM-111 | CY-020 | SI-4 | Evidence or control implementation gap for CY-020 | Low | Vulnerability Scan | Action Owner | 2026-05-22 | 2026-08-20 | -18 | Open | Medium | No | No
POAM-112 | CY-021 | IR-4 | Evidence or control implementation gap for CY-021 | Critical | STIG Review | Action Owner | 2026-05-23 | 2026-06-07 | -19 | Open | High | Yes | Yes
POAM-113 | CY-022 | SC-13 | Evidence or control implementation gap for CY-022 | High | Design Review | Action Owner | 2026-05-24 | 2026-06-23 | -20 | Open | High | No | Yes
POAM-114 | CY-023 | SC-28 | Evidence or control implementation gap for CY-023 | Medium | Test Event | Action Owner | 2026-05-25 | 2026-07-24 | -21 | Mitigated | Low | No | No
POAM-115 | CY-024 | IA-5 | Evidence or control implementation gap for CY-024 | Low | Assessment | Action Owner | 2026-05-26 | 2026-08-24 | -22 | Open | Medium | No | No
POAM-116 | CY-025 | RA-5 | Evidence or control implementation gap for CY-025 | Critical | Vulnerability Scan | Action Owner | 2026-05-27 | 2026-06-11 | -23 | Open | High | Yes | Yes
POAM-117 | CY-026 | CA-2 | Evidence or control implementation gap for CY-026 | High | STIG Review | Action Owner | 2026-05-28 | 2026-06-27 | -24 | Open | High | No | Yes
POAM-118 | CY-027 | CA-7 | Evidence or control implementation gap for CY-027 | Medium | Design Review | Action Owner | 2026-05-29 | 2026-07-28 | -25 | Open | Medium | No | No
POAM-119 | CY-028 | SI-4 | Evidence or control implementation gap for CY-028 | Low | Test Event | Action Owner | 2026-05-30 | 2026-08-28 | -26 | Open | Medium | No | No
POAM-120 | CY-029 | IR-4 | Evidence or control implementation gap for CY-029 | Critical | Assessment | Action Owner | 2026-05-01 | 2026-05-16 | 3 | Mitigated | Low | Yes | Yes
Formulas:
Days Open = IF([Status]="Closed",0,TODAY()-[Open Date])

## IATT Gate
Gate Item | Owner | Entry Criteria | Exit Criteria | Evidence Source | Status | Decision Notes
Boundary defined | System Owner | System boundary draft complete | AO/stakeholder review complete | System Boundary Diagram | In Progress
Initial SSP complete | ISSM | Initial controls selected | SSP contains IATT minimum controls | SSP | In Progress
Initial scan complete | Cyber Lead | Build available for scan | Critical findings documented/mitigated | Scan Results | Not Started
ISA/ICD drafted | Interface Lead | Interfaces identified | Interconnections reviewed for test use | ISA/ICD | In Progress
SAP approved | SCA | Assessment scope defined | SAP accepted for test authorization | SAP | Not Started
SAR draft complete | SCA | Assessment executed | Findings documented and risk ranked | SAR | Not Started
POA&M established | ISSM | Findings loaded | Owners and closure dates assigned | POA&M | In Progress
IATT decision package | PM / ISSM | IATT artifacts complete | AO grants IATT or provides conditions | Decision Package | Not Started

## ATO Gate
Gate Item | Owner | Entry Criteria | Exit Criteria | Evidence Source | Status | Decision Notes
Final SSP complete | ISSM | IATT findings addressed | All operational controls documented | SSP | Not Started
Final vulnerability scan complete | Cyber Lead | Production baseline configured | No unresolved critical/high findings without approval | Scan Results | Not Started
Control assessment complete | SCA | All controls implemented | SAR completed with residual risk | SAR | Not Started
Continuous monitoring plan complete | ISSM | Monitoring sources identified | ConMon approved and scheduled | ConMon Plan | Not Started
Incident response procedures validated | Ops Lead | IR plan drafted | Tabletop/test completed | IR Plan/Test Report | Not Started
Configuration baseline locked | CM Lead | Assets inventoried | Baseline approved and change process active | CM Plan / HW-SW List | Not Started
POA&M adjudicated | ISSM | Open findings reviewed | Residual risk accepted or mitigated | POA&M | Not Started
ATO decision package | PM / ISSM | All ATO artifacts complete | AO grants ATO or conditional ATO | Decision Package | Not Started

## IMS
Task ID | Phase | Task Name | Start Date | Finish Date | Duration Days | Dependency | Owner | Linked CDRL | Linked RMF Step | Milestone
IMS-001 | Prepare | RMF kickoff and stakeholder alignment | 2026-05-01 | 2026-05-15 | 14 |  | PM / ISSM | A001 | Prepare | RMF Start
IMS-002 | Prepare | Define system boundary and authorization boundary | 2026-05-15 | 2026-06-05 | 21 | IMS-001 | System Owner | A002 | Prepare | Boundary Baseline
IMS-003 | Categorize | Security categorization and impact analysis | 2026-06-05 | 2026-06-19 | 14 | IMS-002 | ISSM | A003 | Categorize | Categorization Complete
IMS-004 | Select | Control baseline selection and tailoring | 2026-06-19 | 2026-07-17 | 28 | IMS-003 | ISSM / SCA | A004 | Select | Control Baseline
IMS-005 | Implement | Architecture and control implementation design | 2026-07-17 | 2026-09-04 | 49 | IMS-004 | Engineering Lead | A005 | Implement | Design Complete
IMS-006 | Implement | Network and repository build | 2026-09-04 | 2026-11-27 | 84 | IMS-005 | Engineering Lead | A006 | Implement | Build Complete
IMS-007 | Implement | STIG hardening and configuration baseline | 2026-10-08 | 2026-12-25 | 78 | IMS-006 | Cyber Lead | A007 | Implement | Baseline Locked
IMS-008 | Assess | Initial scans, evidence collection, and test assessment | 2026-11-27 | 2027-02-05 | 70 | IMS-007 | SCA / Cyber Lead | A008 | Assess | Initial Assessment
IMS-009 | Authorize | IATT package assembly and review | 2027-02-05 | 2027-03-27 | 50 | IMS-008 | ISSM / PM | A009 | Authorize | IATT Review
IMS-010 | Authorize | IATT decision milestone | 2027-03-27 | 2027-04-01 | 5 | IMS-009 | AO | A010 | Authorize | IATT
IMS-011 | Implement | IATT condition remediation and operational hardening | 2027-04-01 | 2027-06-25 | 85 | IMS-010 | Engineering / Cyber | A011 | Implement | IATT Conditions Closed
IMS-012 | Assess | Final control assessment and final scan | 2027-06-25 | 2027-08-24 | 60 | IMS-011 | SCA | A012 | Assess | Final Assessment
IMS-013 | Authorize | ATO package assembly and risk adjudication | 2027-08-24 | 2027-10-03 | 40 | IMS-012 | ISSM / PM | A013 | Authorize | ATO Review
IMS-014 | Authorize | ATO decision milestone | 2027-10-03 | 2027-10-08 | 5 | IMS-013 | AO | A014 | Authorize | ATO
IMS-015 | Monitor | Continuous monitoring activation | 2027-10-08 | 2027-11-12 | 35 | IMS-014 | Operations / ISSM | A015 | Monitor | ConMon Active
IMS-016 | Monitor | Recurring POA&M, scan, and artifact maintenance | 2027-11-12 | 2028-04-30 | 170 | IMS-015 | Operations / Cyber | A016 | Monitor | Sustain Authorization

## CDRL IMS Linkage
CDRL ID | Deliverable | DID / Artifact Type | Linked IMS Task | RMF Step | IATT / ATO | Initial Due | Recurring Frequency | Primary Owner | Acceptance / Review Criteria
A001 | RMF Strategy / Cybersecurity Program Plan | Plan | IMS-001 | Prepare | IATT | 2026-05-15 | As updated | ISSM | Approved RMF strategy and roles
A002 | System Boundary Diagram | Architecture | IMS-002 | Prepare | IATT | 2026-06-05 | As updated | System Owner | Boundary and interfaces approved
A003 | Security Categorization Report | Analysis | IMS-003 | Categorize | IATT | 2026-06-19 | As updated | ISSM | Impact level documented
A004 | Control Selection and Tailoring Matrix | Matrix | IMS-004 | Select | IATT | 2026-07-17 | As updated | ISSM | Controls selected and tailored
A005 | System Security Plan | SSP | IMS-005 | Implement | IATT/ATO | 2026-09-04 | Quarterly | ISSM | Implementation statements complete
A006 | Architecture Model / Network Diagrams | Architecture | IMS-006 | Implement | IATT/ATO | 2026-11-27 | As updated | Engineering | Topology aligns to boundary
A007 | Configuration Baseline and STIG Evidence | Evidence | IMS-007 | Implement | IATT/ATO | 2026-12-25 | Quarterly | Cyber Lead | Hardening evidence complete
A008 | Security Assessment Plan | SAP | IMS-008 | Assess | IATT | 2027-02-05 | As updated | SCA | Assessment scope accepted
A009 | Security Assessment Report Draft | SAR | IMS-009 | Assess | IATT | 2027-03-12 | As updated | SCA | Findings documented
A010 | IATT Decision Package | Decision Package | IMS-010 | Authorize | IATT | 2027-03-31 | One-time | PM / ISSM | AO decision or conditions
A011 | POA&M and Remediation Evidence | POA&M | IMS-011 | Implement | ATO | 2027-06-25 | Monthly | ISSM | Findings tracked to closure
A012 | Final Security Assessment Report | SAR | IMS-012 | Assess | ATO | 2027-08-25 | As updated | SCA | Residual risk documented
A013 | Continuous Monitoring Plan | ConMon Plan | IMS-013 | Monitor | ATO | 2027-10-04 | Annual/As updated | ISSM | Monitoring strategy accepted
A014 | ATO Decision Package | Decision Package | IMS-014 | Authorize | ATO | 2027-10-09 | One-time | PM / ISSM | AO ATO decision
A015 | Continuous Monitoring Reports | Report | IMS-015 | Monitor | ATO | 2027-11-13 | Monthly/Quarterly | Cyber Lead | Ongoing metrics reported
A016 | Updated POA&M / Risk Register | POA&M/Risk | IMS-016 | Monitor | ATO | 2027-12-01 | Monthly | ISSM | Risks current and actionable

## Risk Register
Risk ID | Linked Req | Linked Control | Risk Statement | Cause | Impact | Likelihood | Risk Score | Risk Level | Mitigation | Owner | Due Date | Status
R-001 | FTN-001 | SC-7 | If FTN-001 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-22 | Open
R-002 | FTN-002 | SC-8 | If FTN-002 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 2 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-29 | Open
R-003 | FTN-003 | SC-45 | If FTN-003 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 5 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-06 | Open
R-004 | FTN-004 | AU-2 | If FTN-004 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-13 | Open
R-005 | FTN-005 | SI-4 | If FTN-005 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 4 | 16 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-20 | Open
R-006 | FTN-006 | CM-2 | If FTN-006 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-27 | Open
R-007 | FTN-007 | SC-7 | If FTN-007 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 2 | 4 | Low | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-03 | Mitigated
R-008 | FTN-008 | SC-8 | If FTN-008 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 5 | 25 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-10 | Open
R-009 | FTN-009 | SC-45 | If FTN-009 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-17 | Open
R-010 | FTN-010 | AU-2 | If FTN-010 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 4 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-24 | Open
R-011 | FTN-011 | SI-4 | If FTN-011 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-31 | Open
R-012 | FTN-012 | CM-2 | If FTN-012 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 2 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-07 | Open
R-013 | FTN-013 | SC-7 | If FTN-013 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 5 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-14 | Open
R-014 | FTN-014 | SC-8 | If FTN-014 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-21 | Mitigated
R-015 | FTN-015 | SC-45 | If FTN-015 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 4 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-28 | Open
R-016 | FTN-016 | AU-2 | If FTN-016 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-05 | Open
R-017 | FTN-017 | SI-4 | If FTN-017 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 2 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-12 | Open
R-018 | FTN-018 | CM-2 | If FTN-018 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 5 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-19 | Open
R-019 | FTN-019 | SC-7 | If FTN-019 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-26 | Open
R-020 | FTN-020 | SC-8 | If FTN-020 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 4 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-15 | Open
R-021 | FTN-021 | SC-45 | If FTN-021 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-22 | Mitigated
R-022 | FTN-022 | AU-2 | If FTN-022 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 2 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-29 | Open
R-023 | FTN-023 | SI-4 | If FTN-023 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 5 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-06 | Open
R-024 | FTN-024 | CM-2 | If FTN-024 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-13 | Open
R-025 | FN-001 | CM-2 | If FN-001 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 4 | 16 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-20 | Open
R-026 | FN-002 | CM-6 | If FN-002 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-27 | Open
R-027 | FN-003 | SC-8 | If FN-003 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 2 | 4 | Low | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-03 | Open
R-028 | FN-004 | SC-28 | If FN-004 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 5 | 25 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-10 | Mitigated
R-029 | FN-005 | SA-11 | If FN-005 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-17 | Open
R-030 | FN-006 | AC-3 | If FN-006 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 4 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-24 | Open
R-031 | FN-007 | CM-2 | If FN-007 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-31 | Open
R-032 | FN-008 | CM-6 | If FN-008 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 2 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-07 | Open
R-033 | FN-009 | SC-8 | If FN-009 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 5 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-14 | Open
R-034 | FN-010 | SC-28 | If FN-010 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-21 | Open
R-035 | FN-011 | SA-11 | If FN-011 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 4 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-28 | Mitigated
R-036 | FN-012 | AC-3 | If FN-012 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-05 | Open
R-037 | FN-013 | CM-2 | If FN-013 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 2 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-12 | Open
R-038 | FN-014 | CM-6 | If FN-014 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 5 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-19 | Open
R-039 | FN-015 | SC-8 | If FN-015 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-26 | Open
R-040 | FN-016 | SC-28 | If FN-016 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 4 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-15 | Open
R-041 | FN-017 | SA-11 | If FN-017 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-22 | Open
R-042 | FN-018 | AC-3 | If FN-018 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 2 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-29 | Mitigated
R-043 | FN-019 | CM-2 | If FN-019 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 5 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-06 | Open
R-044 | FN-020 | CM-6 | If FN-020 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-13 | Open
R-045 | FN-021 | SC-8 | If FN-021 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 4 | 16 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-20 | Open
R-046 | FN-022 | SC-28 | If FN-022 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-27 | Open
R-047 | DEE-001 | AC-3 | If DEE-001 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 2 | 4 | Low | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-03 | Open
R-048 | DEE-002 | IA-2 | If DEE-002 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 5 | 25 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-10 | Open
R-049 | DEE-003 | SC-28 | If DEE-003 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-17 | Mitigated
R-050 | DEE-004 | SI-10 | If DEE-004 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 4 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-24 | Open
R-051 | DEE-005 | AU-12 | If DEE-005 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-31 | Open
R-052 | DEE-006 | PL-8 | If DEE-006 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 2 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-07 | Open
R-053 | DEE-007 | AC-3 | If DEE-007 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 5 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-14 | Open
R-054 | DEE-008 | IA-2 | If DEE-008 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-21 | Open
R-055 | DEE-009 | SC-28 | If DEE-009 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 4 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-28 | Open
R-056 | DEE-010 | SI-10 | If DEE-010 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-05 | Mitigated
R-057 | DEE-011 | AU-12 | If DEE-011 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 2 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-12 | Open
R-058 | DEE-012 | PL-8 | If DEE-012 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 5 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-19 | Open
R-059 | DEE-013 | AC-3 | If DEE-013 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-26 | Open
R-060 | DEE-014 | IA-2 | If DEE-014 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 4 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-15 | Open
R-061 | DEE-015 | SC-28 | If DEE-015 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-22 | Open
R-062 | DEE-016 | SI-10 | If DEE-016 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 2 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-29 | Open
R-063 | DEE-017 | AU-12 | If DEE-017 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 5 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-06 | Mitigated
R-064 | DEE-018 | PL-8 | If DEE-018 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-13 | Open
R-065 | DEE-019 | AC-3 | If DEE-019 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 4 | 16 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-20 | Open
R-066 | DEE-020 | IA-2 | If DEE-020 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-27 | Open
R-067 | DEE-021 | SC-28 | If DEE-021 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 2 | 4 | Low | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-03 | Open
R-068 | DEE-022 | SI-10 | If DEE-022 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 5 | 25 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-10 | Open
R-069 | DEE-023 | AU-12 | If DEE-023 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-17 | Open
R-070 | DATA-001 | SC-28 | If DATA-001 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 4 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-24 | Mitigated
R-071 | DATA-002 | SC-8 | If DATA-002 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-31 | Open
R-072 | DATA-003 | AU-9 | If DATA-003 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 2 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-07 | Open
R-073 | DATA-004 | AC-6 | If DATA-004 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 5 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-14 | Open
R-074 | DATA-005 | SI-12 | If DATA-005 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-21 | Open
R-075 | DATA-006 | CP-9 | If DATA-006 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 4 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-28 | Open
R-076 | DATA-007 | SC-28 | If DATA-007 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-05 | Open
R-077 | DATA-008 | SC-8 | If DATA-008 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 2 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-12 | Mitigated
R-078 | DATA-009 | AU-9 | If DATA-009 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 5 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-19 | Open
R-079 | DATA-010 | AC-6 | If DATA-010 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-26 | Open
R-080 | DATA-011 | SI-12 | If DATA-011 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 4 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-15 | Open
R-081 | DATA-012 | CP-9 | If DATA-012 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-22 | Open
R-082 | DATA-013 | SC-28 | If DATA-013 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 2 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-29 | Open
R-083 | DATA-014 | SC-8 | If DATA-014 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 5 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-06 | Open
R-084 | DATA-015 | AU-9 | If DATA-015 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-13 | Mitigated
R-085 | DATA-016 | AC-6 | If DATA-016 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 4 | 16 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-20 | Open
R-086 | DATA-017 | SI-12 | If DATA-017 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-27 | Open
R-087 | DATA-018 | CP-9 | If DATA-018 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 2 | 4 | Low | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-03 | Open
R-088 | DATA-019 | SC-28 | If DATA-019 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 5 | 25 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-10 | Open
R-089 | DATA-020 | SC-8 | If DATA-020 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-17 | Open
R-090 | DATA-021 | AU-9 | If DATA-021 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 4 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-24 | Open
R-091 | DATA-022 | AC-6 | If DATA-022 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-31 | Mitigated
R-092 | CY-001 | RA-5 | If CY-001 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 2 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-07 | Open
R-093 | CY-002 | CA-2 | If CY-002 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 5 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-14 | Open
R-094 | CY-003 | CA-7 | If CY-003 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-21 | Open
R-095 | CY-004 | SI-4 | If CY-004 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 4 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-28 | Open
R-096 | CY-005 | IR-4 | If CY-005 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-05 | Open
R-097 | CY-006 | SC-13 | If CY-006 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 2 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-12 | Open
R-098 | CY-007 | SC-28 | If CY-007 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 5 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-19 | Mitigated
R-099 | CY-008 | IA-5 | If CY-008 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-26 | Open
R-100 | CY-009 | RA-5 | If CY-009 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 4 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-15 | Open
R-101 | CY-010 | CA-2 | If CY-010 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-22 | Open
R-102 | CY-011 | CA-7 | If CY-011 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 2 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-29 | Open
R-103 | CY-012 | SI-4 | If CY-012 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 5 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-06 | Open
R-104 | CY-013 | IR-4 | If CY-013 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-13 | Open
R-105 | CY-014 | SC-13 | If CY-014 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 4 | 16 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-20 | Mitigated
R-106 | CY-015 | SC-28 | If CY-015 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-27 | Open
R-107 | CY-016 | IA-5 | If CY-016 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 2 | 4 | Low | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-03 | Open
R-108 | CY-017 | RA-5 | If CY-017 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 5 | 25 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-10 | Open
R-109 | CY-018 | CA-2 | If CY-018 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-17 | Open
R-110 | CY-019 | CA-7 | If CY-019 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 4 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-24 | Open
R-111 | CY-020 | SI-4 | If CY-020 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-31 | Open
R-112 | CY-021 | IR-4 | If CY-021 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 2 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-07 | Mitigated
R-113 | CY-022 | SC-13 | If CY-022 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 5 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-14 | Open
R-114 | CY-023 | SC-28 | If CY-023 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-21 | Open
R-115 | CY-024 | IA-5 | If CY-024 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 4 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-28 | Open
R-116 | CY-025 | RA-5 | If CY-025 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-05 | Open
R-117 | CY-026 | CA-2 | If CY-026 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 2 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-12 | Open
R-118 | CY-027 | CA-7 | If CY-027 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 5 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-19 | Open
R-119 | CY-028 | SI-4 | If CY-028 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-26 | Mitigated
R-120 | CY-029 | IR-4 | If CY-029 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 4 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-15 | Open
R-121 | CY-030 | SC-13 | If CY-030 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-22 | Open
R-122 | INT-001 | SC-7 | If INT-001 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 2 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-29 | Open
R-123 | INT-002 | CA-3 | If INT-002 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 5 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-06 | Open
R-124 | INT-003 | AC-4 | If INT-003 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-13 | Open
R-125 | INT-004 | SC-8 | If INT-004 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 4 | 16 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-20 | Open
R-126 | INT-005 | SC-13 | If INT-005 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-27 | Mitigated
R-127 | INT-006 | SC-7 | If INT-006 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 2 | 4 | Low | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-03 | Open
R-128 | INT-007 | CA-3 | If INT-007 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 5 | 25 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-10 | Open
R-129 | INT-008 | AC-4 | If INT-008 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-17 | Open
R-130 | INT-009 | SC-8 | If INT-009 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 4 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-24 | Open
R-131 | INT-010 | SC-13 | If INT-010 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-31 | Open
R-132 | INT-011 | SC-7 | If INT-011 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 2 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-07 | Open
R-133 | INT-012 | CA-3 | If INT-012 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 5 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-14 | Mitigated
R-134 | INT-013 | AC-4 | If INT-013 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-21 | Open
R-135 | INT-014 | SC-8 | If INT-014 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 4 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-28 | Open
R-136 | INT-015 | SC-13 | If INT-015 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-05 | Open
R-137 | INT-016 | SC-7 | If INT-016 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 2 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-12 | Open
R-138 | INT-017 | CA-3 | If INT-017 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 5 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-19 | Open
R-139 | INT-018 | AC-4 | If INT-018 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-26 | Open
R-140 | INT-019 | SC-8 | If INT-019 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 4 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-15 | Mitigated
R-141 | INT-020 | SC-13 | If INT-020 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-22 | Open
R-142 | OPS-001 | AU-6 | If OPS-001 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 2 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-29 | Open
R-143 | OPS-002 | CM-3 | If OPS-002 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 5 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-06 | Open
R-144 | OPS-003 | CM-8 | If OPS-003 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-13 | Open
R-145 | OPS-004 | CP-10 | If OPS-004 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 4 | 16 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-20 | Open
R-146 | OPS-005 | IR-5 | If OPS-005 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-27 | Open
R-147 | OPS-006 | MA-2 | If OPS-006 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 2 | 4 | Low | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-03 | Mitigated
R-148 | OPS-007 | AU-6 | If OPS-007 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 5 | 25 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-10 | Open
R-149 | OPS-008 | CM-3 | If OPS-008 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-17 | Open
R-150 | OPS-009 | CM-8 | If OPS-009 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 4 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-24 | Open
R-151 | OPS-010 | CP-10 | If OPS-010 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-31 | Open
R-152 | OPS-011 | IR-5 | If OPS-011 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 2 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-07 | Open
R-153 | OPS-012 | MA-2 | If OPS-012 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 5 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-14 | Open
R-154 | OPS-013 | AU-6 | If OPS-013 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-21 | Mitigated
R-155 | OPS-014 | CM-3 | If OPS-014 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 4 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-28 | Open
R-156 | OPS-015 | CM-8 | If OPS-015 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-05 | Open
R-157 | OPS-016 | CP-10 | If OPS-016 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 2 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-12 | Open
R-158 | OPS-017 | IR-5 | If OPS-017 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 5 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-19 | Open
R-159 | OPS-018 | MA-2 | If OPS-018 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-26 | Open
R-160 | SW-001 | SA-10 | If SW-001 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 4 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-15 | Open
R-161 | SW-002 | SA-11 | If SW-002 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-22 | Mitigated
R-162 | SW-003 | CM-5 | If SW-003 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 2 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-06-29 | Open
R-163 | SW-004 | CM-7 | If SW-004 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 5 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-06 | Open
R-164 | SW-005 | SI-7 | If SW-005 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-13 | Open
R-165 | SW-006 | AC-6 | If SW-006 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 4 | 16 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-20 | Open
R-166 | SW-007 | SA-10 | If SW-007 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-07-27 | Open
R-167 | SW-008 | SA-11 | If SW-008 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 2 | 4 | Low | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-03 | Open
R-168 | SW-009 | CM-5 | If SW-009 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 5 | 25 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-10 | Mitigated
R-169 | SW-010 | CM-7 | If SW-010 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 3 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-17 | Open
R-170 | SW-011 | SI-7 | If SW-011 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 4 | 12 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-24 | Open
R-171 | SW-012 | AC-6 | If SW-012 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 3 | 6 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-08-31 | Open
R-172 | SW-013 | SA-10 | If SW-013 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 2 | 10 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-07 | Open
R-173 | SW-014 | SA-11 | If SW-014 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 5 | 20 | Critical | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-14 | Open
R-174 | SW-015 | CM-5 | If SW-015 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 3 | 3 | 9 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-21 | Open
R-175 | SW-016 | CM-7 | If SW-016 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 2 | 4 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-09-28 | Mitigated
R-176 | SW-017 | SI-7 | If SW-017 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 5 | 3 | 15 | High | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-05 | Open
R-177 | SW-018 | AC-6 | If SW-018 is not fully implemented, RMF evidence or mission readiness may be delayed. | Incomplete implementation evidence or configuration variance | 4 | 2 | 8 | Medium | Assign owner, collect evidence, retest, and update POA&M until closure. | Risk Owner | 2026-10-12 | Open

## Source Selection
Offeror | Technical Approach (30%) | Cyber/RMF Approach (25%) | IMS Realism (15%) | Risk Management (15%) | Cost Realism (15%) | Weighted Score | Risk Adjuster | Final Score | Notes
Offeror A | 4 | 4 | 3 | 3 | 4 | 3.7 | 0.95 | 3.515
Offeror B | 3 | 5 | 4 | 4 | 3 | 3.8 | 1 | 3.8
Offeror C | 5 | 3 | 4 | 3 | 4 | 3.9 | 0.95 | 3.705
Offeror D | 4 | 4 | 5 | 5 | 3 | 4.15 | 1 | 4.15
Offeror E | 3 | 3 | 3 | 4 | 5 | 3.45 | 1 | 3.45
Scoring Scale
5 | Excellent / low risk
4 | Good / manageable risk
3 | Acceptable / moderate risk
2 | Marginal / high risk
1 | Unacceptable / very high risk
0 | No confidence / non-responsive

## Diagrams
RMF Process Flow
Prepare → Categorize → Select → Implement → Assess → IATT → Remediate → Final Assess → ATO → Monitor
Traceability Model
SOO Objective → Requirement → NIST Control → Evidence Artifact → Assessment Finding → POA&M → IMS Task → CDRL → AO Decision
Authorization Gate View
IATT: Controlled test authorization with known risk and limited scope
ATO: Full operational authorization with residual risk accepted and continuous monitoring active
System Evidence Flow
Architecture / Boundary → Control Implementation → Scans & Tests → SAR Findings → POA&M → AO Package

## Data Lists
Status | Priority | Verification | RMF Step | Risk Level | Gate | Artifact Status | Finding Status
Not Started | High | Test | Prepare | Low | IATT | Not Started | Open
In Progress | Medium | Inspect | Categorize | Medium | ATO | In Progress | Mitigated
Complete | Low | Demonstrate | Select | High |  | Complete | Closed
Blocked | Critical | Analyze | Implement | Critical |  | Blocked | Accepted
Deferred |  |  | Assess |  |  | Submitted
Accepted |  |  | Authorize |  |  | Approved
Monitor

## Glosary
Term | Description | Resource
Broad Ocean Area (BOA) | BOA will be receiving RV telemetry from a series of boats that will be utilizing SATCOM. | VSFB Test Network Requirements
Cyber Security Services (CSS) | CSS will be in charge of all of the firewalls, taclanes, and providing the AAA services for the network. CSS will be incharge of sending the log files to the CDOC/CSOC | Kevin information?
Data Acquisition and Processing System (DAPS) | DAPS will ingest, time‑stamp, and process telemetry, video, and sensor data from test assets, then forward the cleaned streams into the Test Support Network for real‑time monitoring and archival. | Get in contact with Shannon Farrel
In Silo Instrumentation (ISI) | ISI will collect pressure, temperature, load, and propellant‑flow measurements from inside launch silos and push the data to the network for health monitoring and safety‑abort decision making. | In SIlo Instrumentation CONOPS - Ryan DaVisio
Launch Execution Network (LEN) | The LEN is a network that will be built for flight test launch execution utilizing buildings 8510, 8339, and TP-01 at VSFB.
Launch Support System (LSS) | LSS will manage pre‑launch checklists, resource allocation, and inter‑system handshakes, publishing milestone events (e.g., “Fueling Complete”, “Countdown‑Start”) onto the network for downstream synchronization. | POC contacted.
Pad Launch Electronic Ground Support Equipment (PL EGSE) | PL EGSE will simulate and verify vehicle avionics on the pad, streaming test results and pass/fail status into the network to be correlated with live telemetry | (U)K03NN01352_FT-02_EGSE_Directive(CUI).pptx
Regan Test Site (RTS) | RTS will supply high‑rate radar, lidar, and optical tracking data for ground‑based tests, feeding position and attitude information into the network. | VSFB Test Network Requirements
Western Range Internet Protocol Network (WRIPN) | WRIPN will serve as the | VSFB Test Network Requirements
Pacific Missile Range Facility (PMRF) | PMRF will provide maritime‑range radar, telemetry stations, and video streams from Pacific‑theater tests, routing the data into the network for global situational awareness and post‑test analysis. | VSFB Test Network Requirements
Cyber Defense Operation Center (CDOC) | The CDOC will review the log files of the systems that are connected to the LEN network.